# Introduction

This report discusses the activities, meetings, and results from November and the first weeks of December 2022 for the Social Care Pilot. In particular the finalization of the Excel table with concepts (categories and data) and the start of the use case documents for Mental Health and Alcohol and Substance misuse are the main achievements.

A third meeting with the participants has been carried out with in general support of the approach taken for Mental Health and Alcohol and Substance Misuse. However, requested feedback has been received minimally.

# Activities and meetings carried out

During November and December, the weekly and fortnightly calls were held with the project leads (Jane Millar and Ian Green) to discuss planning, activities, progress, and insights and with Suzy Roy and Cathy Richardson as well, also to prepare for review. Due to busy schedules some calls were skipped.

The Excel table with concepts for elderly care has been finalized for this stage, and Cathy has taken over this table to look at how it can be fitted into SNOMED CT.

The next activity was to start with the Mental Health Use Cases document. Several versions have been handled internally and one version has been discussed with the experts.

Finally the Use Case document for Alcohol and Substance misuse was created and has been discussed

# Second results and impressions

Use Care documents for both additional UC have been created. In both the individual meetings with experts and in the full meeting confirmations were received. Overall, they support that the UCs from Elderly Care apply to Mental Health and to Alcohol and Substance misuse as well. However, particular content for the additional topics include legal issues of different nature (such as permissions, working within legal boundaries, privacy/data exchange blockades, and guardianships) and multidisciplinary teams beyond health and beyond social care, for instance police, community services, child services, among other.

Some of the minutes from meetings with individual experts have been approved, others are underway.

# Planned work

Five selected use cases for Social Care for the pilot Mental Health and Alcohol and Substance misuse have been created. The documents have been sent to experts with requests for comments. This is due 9 and 15th of January. However, an extension was agreed on January 11.

Remind the experts about the meeting minutes and get approval for its contents.

The concept table format in Excel will be created to capture the categories and concepts from the use case(s) for Mental health and alcohol and substance misuse.

The normal meetings will be continued, and the next regular call with the participants is planned for January 19. The agenda for that meeting is roughly going through the Alcohol and Substance document, and when there is time also Mental Health.

A more detailed planning to handle feedback has been discussed on Jan 11 as well.