## Slide 1: Cancer Synoptic Worksheet Encoding Project
Scott Campbell, Jim Campbell IPaLM

## Slide 2: Objective
Create all necessary concepts representative of data elements contained in the 82 College of American Pathologists (CAP) worksheets
  Using CAP as the nominal measuring stick
  RCP, RPCA and ICCR data elements to be included, as well
Use Observables model, clinical findings, body structures, etc and fully define wherever possible
Complete within 15 months
Publish to US NLM and submit to IHTSDO for promotion to core

## Slide 3: Methodology
Use UNMC Namespace and authoring environment
  SnowOwl, Cerner Copath, Epic. Namespace ID = 1000004
Proposed working group tasks:
  Interpret data elements within synoptic worksheets
  Review content developed and advise on accuracy or offer improvements
  Create/Develop concepts (FSN) for worksheets if interested in that aspect
  Act as liaison to national colleges and terminology centers
  Suggest regular meetings/sub-meetings bimonthly

## Slide 4: Work Process
Understand specific worksheet data elements at hand (pathologist assistance critical)
Develop Fully Specified Name (FSN) for concept
Articulate and record defining A-V pairs (Note: some concepts will need to be authored where A-V pairs deficient)
Review proposed concept design
Author terms in SnowOwl
Deploy in Cerner/Epic
Publish to US NLM and elsewhere
  Concepts represented as SCTID’s in Nebraska namespace. IHTSDO/RII to determine ultimate published code (LOINC, SNOMED CT, both?)

## Slide 5: Example – Histology type of neoplasm of breast
Observable FSN | Property Type | Inheres in | Inherent location | Direct site | Technique | Scale | Temporal aspect
Histologic type of excised neoplasm of breast (observable entity) | 373020761000004107¦Morphology (qualifier value)¦ | 367651003¦Malignant neoplasm (mophologic abnormality)¦ | 76752008¦Breast structure (body structure)¦ | 441652008¦Formalin-fixed paraffin-embedded tissue specimen (specimen)¦ | 278289002 ¦Microscopy technique (qualifier value)¦ | 117362005¦Nominal value (qualifier value) | 123029007¦ Single point in time(qualifier)¦

## Slide 6: New Concept Authoring

## Slide 7: Value Set – Histologic types (example)
Histologic Type of neoplasm of breast | 138659001000004102¦ Histologic type of breast neoplasm (observable entity)¦ |  | 
 |  | Invasive mammary carcinoma of no special type | 82711006 ¦ Infiltrating duct carcinoma (morphologic abnormality) ¦
 |  | Micro-invasive mammary carcinoma | 443933007 ¦ Ductal carcinoma in situ with microinvasion (morphologic abnormality) ¦
 |  | Invasive mammary carcinoma with extensive intraductal component | 373395001 ¦ Invasive ductal carcinoma with an extensive intraductal component (morphologic abnormality) ¦
 |  | Invasive mammary carcinoma with matrix production | 729164801000004106¦Carcinoma with matrix production (morphologic abnormality)¦
 |  | Invasive lobular carcinoma | 89740008 ¦ Lobular carcinoma (morphologic abnormality) ¦
 |  | Invasive mammary carcinoma, no special type, with lobular features | 857447761000004107¦Carcinoma with lobular features (morphologic abnormality)¦
 |  | Invasive lobular carcinoma with pleomorphic features | 861026411000004109¦Lobular carcinoma with pleomorphic features (morphologic abnormality)¦
 |  | Invasive lobular carcinoma, alveolar variant | 605862111000004109¦Lobular carcinoma, alveolar variant (morphologic abnormality)¦
 |  | Invasive carcinoma with ductal and lobular features ("mixed type carcinoma") | 444057000 ¦ Infiltrating carcinoma with ductal and lobular features (morphologic abnormality) ¦

## Slide 8: To be discussed:
Feedback on proposed approach
Who is interested in assisting as part of working sub-group
  Level of participation?
Issues with extensibility outside of U.S.?
Suggested frequency of meetings

## Slide 9: Next Steps:
Prioritize tissue pathways/worksheets
Develop specific work schedule
Assign tasks