# IHTSDO Content development work item - Proposal

# Title

ICNP to SNOMED CT Nursing Diagnostic Problem Concepts: Content Development and Refset

## Version Information

| Document Author(s): | Susan Matney, Zac Whitewood-Moores, Amy Coenen |
| --- | --- |
| Proposer: | Nursing Special Interest Group |
| Version: | 1 |
| Date Created: | 3/06/2014 |
| Document status | Draft |

## Document review – for usage by Healthcare Professional group when agreeing proposal

| #### Reviewer | #### Review date | #### Comment |
| --- | --- | --- |

## Proposed business purpose supported by development

Requestors have identified various needs for the mapping ICNP to SNOMED CT concepts, including to:

- Provide a smooth path for the integration of SNOMED CT into the nursing domain, by connecting it to a nursing specific terminology with broad international acceptance and use.

- Allow for continued use of ICNP, while also enabling the integration within and interoperability between EHRs of nursing data through SNOMED CT as a reference terminology.

- Leverage an industry standard equivalency table, as opposed to every user creating a separate map, at great expense to the industry and with significant risk for inconsistency and errors in mapping.

This problem list refset may be used as a pick-list within systems by nurses to document the nursing diagnosis/problem. Within the U.S., this refset will meet the mandated criteria for the documenting a problem on the patient’s care record. In other countries, the refset can facilitate system developers and nurses to select nursing content for EHR applications. The ICNP problem concepts are developed to be consistent with the ISO 18104: Categorial structures for representation of nursing diagnoses and nursing actions in terminological systems.

## Statement of Problem or Need

Nurses make up  the largest number of healthcare professionals  and are required to document nursing problem(s) as part of the nursing process. There is currently no international SNOMED CT nursing refsets available for nursing problems. The International Council of Nurses (ICN) has a formal Harmonisation Agreement with IHTSDO to ‘to advance terminology harmonization and foster interoperability in health information systems’. The ICN develops and maintains the ICNP, which includes content for problems diagnosed by nurses.

This project supports two of the IHTSDO’s strategic priorities to 2015:

1. Make it easier to use SNOMED CT for priority use cases

3. Facilitate use of SNOMED CT with other international standards

## Proposed work summary description

This work is a collaborative effort with the International Council of Nurses (ICN). The project will consist of two phases 1) the addition of ICNP nursing problems that do not exist in SNOMED CT; and 2) the creation of the nursing problem refset.

Future projects will focus on ICNP content for nursing interventions and patient outcomes or goals.

## Objectives

To promote and support implementations of SNOMED CT in clinical systems used by nurses through the provision of a maintained equivalency table between  pre-coordinated diagnostic concepts  in ICNP and clinical findings in SNOMED CT. NOTE we are only providing equivalent concepts in the refset (not mappings such as “narrower” or ‘broader”)

<Define the specific Objectives of the proposed work that correlate to the IHTSDO strategic initiatives.  Every objective must relate to at least one strategic initiative >

| IHTSDO Strategic Plan - Use case | Proposed work objective |
| --- | --- |
| Use Case #1 | Broaden the use of SNOMED CT, within and across health information systems, countries and professions. |
| Use Case #2 | Cost effective technologies exist that enable SNOMED CT to be used with other international terminologies and classifications |
| Use Case #3 |  |
| Use Case #4 |  |

## Associated timelines for completion of work

<Outline proposed timelines for undertaking the work and the reason for the timelines i.e. the drivers. These must be from an international perspective>

March 15, 2014: ICN delivers: (a) equivalency table of ICNP-SNOMED CT problems and (b) table of concepts recommended for submission to complete refset

March 18, 2014: Nursing SIG review table and prepares for submission as a refset

April  15, 2014: Submission of nursing problems from ICNP and SNOMED CT concepts needed for the ref set.

Identified risks associated with development

<Internal and external>

| Risk Item | Risk Level Range |  |  | Comments |
| --- | --- | --- | --- | --- |
|  | High | Medium | Low |  |
| External Dependencies Risk How dependent is the development on other projects or work items? | 11-15 | 6-10 | 1-5 |  |
| Mission Critical Risk How critical is the project success in the success of SNOMED CT internationally | 11-15 | 6-10 | 1-5 |  |
| Failure Risk What is the risk of failure? | 11-15 | 6-10 | 1-5 |  |

Stakeholder input

<Evidence of requests or requirements from users/stakeholders, and evidence they agree with proposed development>

Nurses and software vendors have requested a mapping of ICNP nursing diagnoses/outcomes and interventions over the past ten years.  Various mappings of these terminologies exist, having been created locally.  Since posting the ICN equivalency table of ICNP Diagnoses and SNOMED CT concepts in October 2013, more than 50 files were downloaded by users in XX countries.