# Project Description

# To be completed by proposers of projects/ideas for initiatives deemed promising in a preliminary review at the Committee level.

| Working Group Information |  |  |  |
| --- | --- | --- | --- |
| Name of Working Group | Name of Working Group Chair |  |  |
| Nursing Special Interest Group | Anne Casey |  |  |
| Signature of Chair | Date Submitted to IHTSDO Office |  |  |
| General Information |  |  |  |
| Project Title Canadian Health Outcomes for Better Information and Care (C-HOBIC) & International Classification for Nursing Practice (ICNP) SUBSET PROJECT |  |  | Proposed by Kathryn Hannah - Canada Claudia Bartz - International Council of Nurses (ICN) |
| Potential Project Manager Kathryn Hannah |  |  | Potential Project Owner Jontly owned by Nursing SIG and ICN |
| Proposed start date June 2010 |  |  | Proposed End date December 2010 |
| Summary This exploratory project instantiates the harmonisation agreement between the IHTSDO and ICN. It will investigate potential approaches to harmonisation of ICNP subset content and SNOMED-CT whilst meeting the requirements of national member body (Canada) for SNOMED CT mapped with ICNP outcome concepts using the C-HOBIC standard (see background below). An additional aim of the project is to test the use of ICN’s web-based collaborative toolset (C-Space) for ongoing harmonisation work with IHTSDO. |  |  |  |
| Context |  |  |  |
| Background (Edited extract from JAMIA 2009;16:524 –530). The Canadian Health Outcomes for Better Information and Care (C-HOBIC) project introduced systematic use of standardized clinical nursing terminology for patient assessments. Initially implemented in three Canadian provinces, C-HOBIC comprises an innovative model for large-scale capture of standardized nursing sensitive clinical outcomes data within electronic health records (EHRs). To support this activity, nursing assessment and outcome concepts were mapped to the International Classification for Nursing Practice (ICNP). The importance of the project The C-HOBIC model provides standardized, consistent, interoperable clinical information that reflects nursing practice throughout the Canadian healthcare system. C-HOBIC is supported at government level for the comparison of serial data on a patient across multiple time points and settings, providing nurses with information critical to planning for and evaluating patient care. The availability of the standard model supports inclusion of nursing information in EHRs presently in three provinces and ultimately in all provinces of Canada. However, there will be interoperability challenges when future EHRs use SNOMED CT unless it is also possible to represent the C-HOBIC / ICNP subset e content using SNOMED CT. Problems solved through this project - Future interoperability challenges related to nursing data in EHRs in Canada and potentially in other IHTSDO national member countries. - Lack of effective methods for engaging nursing and other healthcare professions in development and review of SNOMED CT derivative work such as subset development. - Clarification of an operational process would be one aspect of the work of IHTSDO/ICN Harmonisation Board and potentially that of other, future Harmonisation Boards. |  |  |  |
| Target Immediate beneficiaries of the project are: - Canada – EHR suppliers and nursing community (individual users of ICNP can leverage an industry standard map, as opposed tousers doing their own maps, with great expense to the industry and with greater risk for inconsistency and error). - IHTSDO – ICN Harmonisation Board and Community of Practice (C-HOBIC will be widely used and will be implemented using ICNP – a mapping will significantly widen the reach of SNOMED CT without any need for additional local terminology support. Nurses in Germany are already asking to use the C-HOBIC ICNP subset. F A SNOMED-CT mapping of this catalogue could enhance awareness of SNOMED CT in that country. - International Council of Nurses - a mapping will allow for the continued use of ICNP, while enabling the integration within and interoperability between EHRs of normalized nursing data through the broader SNOMED CT reference terminology . |  |  |  |
| Content |  |  |  |
| - The first (external) phase of the project is under way - development and validation of the C-HOBIC / ICNP subset which contains <100 observables with associated scale values. - Informal review of the subset content by SNOMED CT expert to inform and scope the concept matching exercise. - Concept matching exercise by C-HOBIC, ICNP and SNOMED CT experts. - Validation by independent reviewers using ICN C-Space. - Preparation and quality review of an IHTSDO Guideline document and Technical Report. |  |  |  |
| Fit with IHTSDO strategy (Strategic Direction to 2015) Supports: - shared goal in strategic priority 1b - shared goal in strategic priority 2c - shared goal in strategic priority 3b - strategic priority 4b Also relates to strategic priority 1c through trial use of alternative mechanism for engaging wider clinical community in IHTSDO activity. |  |  |  |
| Deliverables - An IHTSDO Guideline which specifies the SNOMED CT descriptions and concept codes that are recommended for use when implementing the C-HOBIC / ICNP subset in systems. The Guideline will include the approach to distribution, maintenance and review of the subset. - A Technical Report on the method used, lessons learned, etc. with recommendations for the Management Board / Communtiy of Practice on engagement of clinical professionals in IHTSDO activity. |  |  |  |
| Risks and Proposed mitigation Availability of expertise to complete the project; Maintain commitment from Canada, ICN and Nursing SIG members. Lack of uptake of the completed Guideline; Plan communication strategy with ICN and Canadian leads (impacted by readiness of system suppliers to implement SNOMED CT). |
| Project organization and environment |  |  |  |
| Project owner – joint owners are Canada, ICN and IHTSDO Nursing SIG Leader - Kathryn Hannah Participants – Nursing SIG members, users of ICN C-Space, C-HOBIC experts in Canada The Project will report to I&I Committee via the Nursing SIG. A reference group is not required as the members of the Nursing SIG have relevant expertise. Members directly engaged with this project: Amy Coenen, Nicholas Hardiker, Tae Youn Kim, Claudia Bartz (ICN staff/ICNP experts); Zac Whitewood-Moores, Anne Casey (SNOMED CT expertise) |  |  |  |
| Interested parties C-HOBIC (which was previously funded by Canada Health Infoway, Canadian Nurses Association), ICN, IHTSDO Nursing SIG. The participation of key interested parties is already assured. Expectations of ICN and the Nursing SIG relate to the pilot test nature of this project. The Guideline is expected to be of value in the future; review and trial use will enhance its usefulness over time. The Technical Report is expected to provide experience-based directions for approaches to harmonisation activity between the IHTSDO and ICN and perhaps between other organisations harmonised with IHTSDO. Canadian stakeholders: the IHTSDO Guideline can inform Canadian stakeholders about implementation of C-HOBIC in EHRs across systems and settings. The SNOMED CT mapping of the C-HOBIC / ICNP subset will foster dissemination and uptake of SNOMED CT among nurses in Canada. |  |  |  |
| Communication strategy External communications will be managed by the organisations involved and their respective constituents. Within IHTSDO, monthly updates will be provided to the Nursing SIG membership. Bi-monthly updates will be provided to the I&I committee by the Chair of the Nursing SIG. Consultation phases and the availability of the completed deliverables will be publicised on the IHTSDO and ICN websites. Communications in Canada will be managed by Canadian lead. |  |  |  |
| Plan and key milestones |  |  |  |
| Project Milestones - Proposal idea presented to the Nursing SIG October 2009 (received approval). - Formal proposal presented to the Nursing SIG April 2010 and submitted to I&I committee end April 2010. - Draft subset provided by ICN for informal review by end June 2010. - Draft Guideline produced by end July 2010 - Consultation on draft Guideline via C-Space August – October 2010 (ICN subset publication anticipated September 2010). - Review and validation at Toronto IHTSDO meeting October 2010. - Draft Technical Report produced by end November 2010. - IHTSDO approvals sought beginning December 2010. Process for reporting on progress and results - Monthly progress on the Nursing SIG Collaborative WorkSpace. - Results will be reported at October 2010 and April 2011 IHTSDO meetings. Process for conducting the project: - Informal review of draft catalogue to identify concept types, clarify definitions if necessary and develop the concept matching strategy. - Concept matching by 2 independent reviewers – paper exercise using CLUE browser. - Independent expert review of all concepts and against agreed strategy. - Consensus meeting (virtual) to address inconsistencies. - Adaptation of C-Space for consultation phase – wide notification of consultation. - Disposition of consultation comments using consensus process; revision of draft Guideline. - Review / validation: paper exercise at face to face meeting; revision of draft Technical Report. - IHTSDO consultation phase with disposition and revision. |  |  |  |
| Quality measures |  |  |  |
| Documented evidence of conformance to IHTSDO development process standards for guidelines and technical reports. Subset quality metrics. All concepts in source set represented in subset. 2.100% consensus on accuracy of matches by independent experts (following consensus exercise). 3.Participants in consultation phases qualified for work by education/experience.4. Final C-HOBIC / ICNP subset published. 5. Guideline published. 6. Technical Report published. |  |  |  |
| Resources |  |  |  |
| IHTSDO resources requested Contract for adaptation of ICN collaborative toolset (C-Space): $3,500 Meeting costs: teleconferences x 3; half day face to face at October 2010 IHTSDO meeting (~ 8 participants) |  |  |  |
| Name of IHTSDO resources requested |  |  |  |
| Other significant resource requirements Volunteer expertise from: Canada, ICN, RCN, NHS. 8 people expected to contribute 5 working days per person over the 6 month project. Other Nursing SIG members have agreed to volunteer time for consultation and assistance with validation of the subset. |  |  |  |
| IHTSDO Confirmation of Report Received |  |  |  |
| Comments |  |  |  |
| Name |  | Position |  |
| Signature |  | Date |  |