# Project Brief – International review of skin & wound assessment concepts

# DRAFT 26 April 2011, updated 10 May, 02 June

# Background

A set of concepts for representing skin and wound assessments was developed as part of an information modeling project led by the US Veterans Administration and including nursing domain experts, Kaiser, Mayo, Partners HC, Aurora HC, IHTSDO, LOINC, HL7, etc. Term binding work by the project team resulted in a request for a number of concepts to be added to SNOMED CT - these are being included in the US extension (July 2011) to meet the external project timelines. This international review is being undertaken on the recommendation of IHTSDO Implementation and Innovation (I&I) committee.

| Project Name: | International review of skin & wound assessment concepts |  |
| --- | --- | --- |
| Deliverables | D1. Endorsement for international use of the set of skin and wound assessment concepts developed by the (US) external project. D2. Communication / guidance materials NOTE: ICN team will consider suitability as ICNP catalogue |  |
| Objectives | - Ensure the quality of SNOMED CT content related to skin & wound assessment - Promote international use / awareness of SNOMED CT by nurses |  |
| Interdependencies / Risks | Time dependency: The content produced by the external project is already being progressed into the international release (Jan 2012) via the US release centre. Risk: Volunteer effort may affect rigour of review |  |
| Benefits for the IHTSDO / relationship to strategic plan and other IHTSDO work: | See IHTSDO project description |  |
| Scope & boundaries - what is and is not included | Included: review for professional acceptability, accuracy and completeness of all concepts in the spreadsheet provided by the external project team i.e. concepts specified by the clinical LOINC nursing subcommittee in partnership with US clinical experts and health care organisations. Not included: technical / editorial policy review |  |
| Project method | - Open invitation for comment via SIG pages and ICNP C-space - Systematic review against concepts identified in international professional literature - Review against existing international terminologies / classifications that cover scope (observation data for skin and wound assessment, including pressure ulcer risk assessment) including: ICNP; NANDA, ICD &. national modifications e.g. Canada; others? - Produce Report and Recommendations |  |
| Quality Assurance Plan | To be developed with reference to ICNP catalogue approach and ICPC map project which includes international professional assurance aspects. |  |
| Communications Plan | Who needs to be involved? Internal stakeholders: IHTSDO WGs: Translation and Primary care via TBD External partners – external project group via Holly, Susan et al Who needs to be informed? I&I committee via Jane Miller Content Committee via Anne Casey Communications products: IHTSDO project description – to I&I and Content Committees Nursing SIG project brief – to other internal stakeholders and external partners Executive Summary / Report – circulation to be decided |  |
| Timescales: | Lam to provide close date for batch submissions January 2012 international release See detailed schedule |  |
| Project Team: | Project Lead: Holly | Email: |
|  | Team: Donna DuLong, Nick Hardiker, Cyndie Lundberg, Susan Matney Anne Casey More volunteers wanted |  |
| Resources - time and money | Days: Meetings / Travel: Consumables: |  |

10 May 2011 Notes: The RCN advises that European Pressure Ulcer Advisory Panel www.epuap.org/ is main international professional group. Their website lists links to 22 national and international organisations related to wounds. There is a world union of wound healing societies which has issued consensus statements including one on diagnostics and wounds http://www.wuwhs.org/datas/2_1/10/Diagnostic_3M_English_WEB.pdf

There are several international professional dermatology associations including International Society of Dermatology http://www.intsocderm.org/i4a/pages/index.cfm?pageid=1 which also has links to national and international dermatology organisations.

There is an International Skin care Nursing Group http://www.isng.org/index.php and many countries have skin care / wound care / dermatology nursing organisations.

It was agreed that national and international groups would not be involved directly but that their standards would be used as evidence for assurance.