# Project Brief – International review of skin & wound assessment concepts

# DRAFT 26 April 2011

# Background

A set of concepts for representing skin and wound assessments was developed as part of an information modeling project led by the US Veterans Administration and including nursing domain experts, Kaiser, Mayo, Partners HC, Aurora HC, IHTSDO, LOINC, HL7, etc. Term binding work by the project team resulted in a request for a number of concepts to be added to SNOMED CT - these are being included in the US extension (July 2011) to meet the external project timelines. This international review is being undertaken on the recommendation of IHTSDO Implementation and Innovation (I&I) committee.

| Project Name: | International review of skin & wound assessment concepts |  |
| --- | --- | --- |
| Deliverables | D1. Endorsement for international use of the set of skin and wound assessment concepts developed by the (US) external project. D2. Communication / guidance materials Question for ICN – could this project also meet the criteria for an ICNP catalogue as a further deliverable? |  |
| Objectives | - Ensure the quality of SNOMED CT content related to skin & wound assessment - Promote international use / awareness of SNOMED CT by nurses |  |
| Interdependencies / Risks | Time dependency: The content produced by the external project is already being progressed into the international release (Jan 2012) via the US release centre. Risk: Volunteer effort may affect rigour of review |  |
| Benefits for the IHTSDO / relationship to strategic plan and other IHTSDO work: | See IHTSDO project description |  |
| Scope & boundaries - what is and is not included | Included: review for professional acceptability, accuracy and completeness of all concepts in the spreadsheet provided by the external project team i.e. concepts specified by the clinical LOINC nursing subcommittee in partnership with US clinical experts and health care organisations. Not included: technical / editorial policy review |  |
| Project method | - Open invitation for comment via SIG pages and ICNP C-space - Systematic review against concepts identified in international professional literature - Review against existing international terminologies / classifications: ICNP; NANDA, ICD incl. national modifications e.g. Canada; others? Question for Donna et al: Are interventions in the set (which would add procedure classifications to scope). - Review against existing system content – targeted invitation to vendors / users of systems with international scope. |  |
| Quality Assurance Plan | To be developed Question for ICN: what criteria are used for catalogue assurance? Anne to ask Jane Miller IHTSDO quality officer about similar projects |  |
| Communications Plan | Who needs to be involved? Anne to ask RCN international officer about international skin / wound professional groups SIG members with NNA affiliations to ask about national skin / wound professional groups IHTSDO WGs: Translation, Primary care, Others? Who needs to be informed? I&I committee via Lam |  |
| Timescales: | Lam to provide close date for batch submissions January 2012 international release Holly and Anne to prepare timeline with actions |  |
| Project Team: | Project Lead: Holly | Email: |
|  | Team: Donna DuLong, Nick Hardiker, Cyndie Lundberg, Jonathan Evans, Susan Matney More volunteers wanted |  |
| Resources - time and money | Days: Meetings / Travel: Consumables: |  |