Updated Description of Project: Skin and wound assessment concepts

| Working Group Information |  |  |
| --- | --- | --- |
| Name of Working Group | Name of Working Group Chair |  |
| Nursing Special Interest Group | Anne Casey |  |
| Signature of Chair | Date Submitted to IHTSDO Office |  |
| General Information |  |  |
| Project Title Skin and wound assessment term international review | Proposed by Nursing SIG |  |
| Potential Project Manager Holly Miller | Potential Project Owner Nursing SIG |  |
| Proposed start date: revised to Jan 2012 | Proposed End date: October 2012 |  |
| Objective/goal |  |  |
| 1. improve content in international release related to skin and wound assessment 2. share lessons from international professional review |  |  |
| Background |  |  |
| The Skin and Wound Information Modeling project led by the Veterans Administration was reported to the Nursing SIG meeting in October 2010 and was noted to be ‘an excellent example of a replicable, collaborative process’. Partners included nursing domain experts, Kaiser, Mayo, Partners HC, Aurora HC, SNOMED CT, LOINC, HL7, NLM, etc see http://pressureulcerpreventionmodel.com/Reconciled/ Term binding work led to some requests for new content through the US. T he I&I Committee recommended that there be an international professional review of this content. The SIG clarified that it would not review the technical modelling of term requests but rather identify whether the content was consistent with international professional practice standards. |  |  |
| Connection with the strategy of the IHTSDO |  |  |
| This project will support the following strategic priorities: - Make it easier to use SNOMED CT for priority use cases - Facilitate use of SNOMED CT with other international standards - Engage clinical professionals in IHTSDO activity |  |  |
| Key deliverables |  |  |
| D1 – Criteria for international professional review of proposed content D2 – Endorsement of content by IHTSDO Nursing SIG D3 - Technical Report on the collaboration, lessons learned, etc. with recommendations for the Management Board / Community of Practice |  |  |
| Target group and external impact |  |  |
| Target groups: IHTSDO Community of Practice; Partners in the Skin and Wound Information Modeling project; International Nursing Community |  |  |
| Possible relation to other IHTSDO Projects |  |  |
| Nursing specific guidance project – in development Request submission project Other Modeling projects involving IHTSDO members |  |  |
| Resourcing - rough order of magnitude |  |  |
| Volunteer effort to review concepts against professional guidelines and against existing terminologies |  |  |
| Other Significant resources requirements : Volunteer effort to produce Technical Report |  |  |
| IHTSDO Confirmation of Report Received |  |  |
| Comments |  |  |
| Name |  | Position |
| Signature |  | Date |