| Work Item | Description | Status | Progress | Notes / next steps |
| --- | --- | --- | --- | --- |
| C-HOBIC [Canadian Health Outcomes for Better Information and Care] C-HOBIC data set was approved as a Canadian standard in Jan 2012. C-HOBIC to ICNP equivalence table was published in 2011. | Development and review of concept equivalence tables - an exploratory work to support future implementation of C-HOBIC in SCT enabled systems. | Ongoing | Draft tables completed for C-HOBIC a) observables b) clinical findings Validation of draft C-HOBIC observables was completed at a workshop hosted by Canada Health Infoway in June 2012. | Validation of draft C-HOBIC findings to be completed - electronic methods. Technical Report to be completed. Both tasks awaiting volunteer resource. |
| Skin and Wound assessment terms review | To review proposed Skin and Wound assessment term bindings proposed by external collaborating organisations (HL7, LOINC etc) from an international nursing perspective. | Ongoing | - Plan to carry out reviews from both professional and terminology perspectives. - Feedback received from Australia and UK - Discussions on potential outcomes of the review at October 2012 meeting. | Limited results - difficulty recruiting volunteer reviewers as well as difficulties obtaining materials in shareable format. |
| NLM nursing problem list subset | Development and maintenance of a ‘semantically interoperable nursing problem list that can be shared across information systems’. | Ongoing - Maintenance phase | Development completed and Technical Report produced. Biannual maintenance review in collaboration with NLM. |  |
| ICNP nursing diagnosis subset | SIG review of concept equivalence tables produced by ICNP team for improved integration in UMLS | Ongoing | Limited - volunteer effort and access issues. | Potential for future RefSet |
| ICNP nursing interventions subset | SIG review of concept equivalence tables produced by ICNP team for improved integration in UMLS | Ongoing | No progress | Potential for future RefSet |
| Review of content related to nursing terminology maps | Consultant terminologist programme project with input from SIG to review whether content conforms to current editorial policies. | Ongoing | - Background information supplied to project lead - Mapping tables for non-proprietary terminologies supplied by CAP - Historical documentation of the modelling heuristics reviewed - Initial review of CCC and OMAHA-related s content identified the main issue: all possible precoordinated content was added to support mapping of these two multi-axial terminologies – not just the clinically sensible content. - SIG review of content tables for ambiguity of descriptions outside context of source - to be reported at October 2012 meeting. | Preliminary results at October meeting |
| Collation of outputs from previous SIG projects | 1. Historic documents collated and uploaded to collaborative site for reference. 2. preparation of inception / elaboration phase documents for Content Committee for items that have not been followed through. | Ongoing | Documents have been identified and collected together. Needs resource to complete. |  |
| Concept model input / concept clarification’ | Input / Responses to: - IHTSDO consultations - ad hoc requests - other WGs | Ongoing | BUSINESS AS USUAL. Currently on the agenda: - Catheter / cannula - Observables model (non-lab) - Content development policy and process - Role and function of SIGs |  |
| Harmonisation with Internal Council of Nursing (ICN) | Evolving relationship with nursing’s international professional organisation (also developer of ICNP terminology) | Ongoing | IHTSDO / ICN collaborative agreement 2010. Latest update to Management Board June 2012 reporting joint activity and raising questions about potential joint products - for discussion during October 2012 meeting. |  |