Nursing SIG Minutes 2013-19-17

Regrets;

Zac Whitewood-Moores

Attendees:

Susan Matney

Amy Coenen

Claudia Bartz

Judy Warren

Anne Casey

Vivian Auld

Elaine ??

Kathryn Hannah

Declaration of interest - none

Minutes approval – Moved by Judy, Elaine seconded

- ICF to SNOMED CT gap analysis project – Susan

  - Judy stated that observables has two separate meetings during the face-to-face to discuss observables both lab and clinical. Mon 10/71:30-5, Weds 10/9 9-12:30

  - Susan will attend observables.

  - Event condition and episode

- ADL/functional abilities area of SNOMED CT – review of Zac’s document

- C-HOBIC next steps plan – Kathryn/Anne

  - Electronic review is complete.

  - Anne and Zac currently compiling comments

  - Comments will be presented in October.

    - Good agreement on a majority of them

    - Those that require resolution will be in a ppt presentation for discussion.

  - Will be ready to go forward to content committee after that.

  - The process has been constructive and is worth noting and acknowledging.

    - Could possibly be a manuscript for nursing.

- ICNP mapping review and strategy for getting into SCT – Susan

  - Susan emailed content committee regarding missing content, will give to them after face-to-face

  - Mappings as well as what doesn’t map will be reviewed.

  - Validation group being pulled together to review mappings

  - Content committee has this project on their agenda.

- Nursing Problem Subset Internationalization Plans– Susan/Judy/Amy

  - Project plan to go to content committee after face-to-face

  - Double check regarding inception document – needs to be done.

    - Review project document Amy created.

  - Susan find out what documents need to be created- check with Kent/Jane.

  - UMLS subset release will be after November 2013.

  - Four projects:

    - ICNP mapping validation

    - New nursing content into SNOMED CT based on missing ICNP mappings to SCT.

    - Nursing problem subset for international use

    - C-HOBIC subset

- Professional SIG Coordination Group  - First meeting report

  - Jane Millar overseeing coordination of SIGs

  - Prepare slide deck showing nursing SIG working

    - I will we can share.

- ICNP IHTSDO Public Good Agreement and mapping validation- Amy

- October Agenda

Meeting scheduled for Sunday, October 6th.

- Overview of past projects

- Meeting Items:

  - C-HOBIC 10:00

  - ICNP mapping review validation and strategy for getting into SCT

  - ADL/functional abilities

  - Review work items

  - UK demonstrate how SNOMED CT is used for care planning OR C-CDA HL7 care plan(Zac and Lauren Heerman Langford)

- LOINC/SNOMED Agreement – LOINC mtg report – Susan

  - LOINC answers possibly coded with SNOMED CT codes

  - Nursing landing page on LOINC website.

- Educational materials for Universities and nurses wanting to learn SNOMED CT.

  - Add to agenda in face-to-face

  - Discuss competencies particular to nursing.

  - Canadian schools of nursing developed national competencies.

    - Kathryn will share.

    - U.S. QSEN (quality

    - ANA revising competencies.

    - Look at IHTSDO website (NEHTA video presentation – 2 part)

    - David Markwell trainings – discuss with Ed SIG

- AOB - none