| SNOMED CT Content Improvement Project Inception phase |  |  |
| --- | --- | --- |
| Project ID: <id> Topic: Functional status and activities of daily living concepts |  |  |
| Date | 2013-08-16 |  |
| Version |  | 0.01 |

Amendment History

| Version | Date | Editor | Comments |
| --- | --- | --- | --- |
| 0.01 | 2013-08-16 | Zac Whitewood-Moores | First draft for comments |
|  |  |  | (remove or add rows if necessary) |

Review Timetable

| Review date | Responsible owner | Comments |
| --- | --- | --- |
| 2013-08-30 | Nursing SIG | Review of first draft |
|  |  | (remove or add rows if necessary) |

© International Health Terminology Standards Development Organisation 2012. All rights reserved.

SNOMED CT® was originally created by the College of American Pathologists.

This document forms part of the International Release of SNOMED CT® distributed by the International Health Terminology Standards Development Organisation (IHTSDO), and is subject to the IHTSDO’s SNOMED CT® Affiliate Licence. Details of the SNOMED CT® Affiliate Licence may be found at http://www.ihtsdo.org/our-standards/licensing/.

No part of this document may be reproduced or transmitted in any form or by any means, or stored in any kind of retrieval system, except by an Affiliate of the IHTSDO in accordance with the SNOMED CT® Affiliate Licence. Any modification of this document (including without limitation the removal or modification of this notice) is prohibited without the express written permission of the IHTSDO.

Any copy of this document that is not obtained directly from the IHTSDO [or a Member of the IHTSDO] is not controlled by the IHTSDO, and may have been modified and may be out of date.  Any recipient of this document who has received it by other means is encouraged to obtain a copy directly from the IHTSDO [or a Member of the IHTSDO. Details of the Members of the IHTSDO may be found at http://www.ihtsdo.org/members/].

Table of Contents

1 Glossary	5

1.1 Domain Terms	5

2 Introduction	6

2.1 Purpose	6

2.2 Audience	6

2.2.1 Identification of stakeholders	6

2.2.2 Input from stakeholders	6

2.2.3 Degree of consensus on the statement of problem	7

3 Statement of the problem or need	7

3.1 Summary of problem or need, as reported	7

3.1.1 Typical current patterns in SNOMED CT	7

3.1.2 Typical representation in C-HOBIC	10

3.2 Summary of requested solution	10

3.3 Statement of problem as understood	11

3.4 Detailed analysis of reported problem, including background	11

3.5 Subsidiary and interrelated problems	12

4 Risks / Benefits	12

4.1.1 Risks of not addressing the problem	12

4.1.2 Risks of addressing the problem	12

5 Requirements: criteria for success and completion	13

5.1 Criteria for success/completion	13

5.2 Strategic and/or specific operational use cases	13

5.2.1 Use case 1 – Falls prevention service care management	13

5.2.2 Use case – Long term condition care management	13

6 Outline Possible Technical Approaches and Concept Model	14

6.1 Indicative Solutions	14

6.1.1 Approach One – create high level concepts and enhance modeling by adding IsA relationships	14

6.1.2 Approach Two – Detailed modeling of each concept to enhance quality	14

6.1.3 Approach Three – Creation of new content and harmonization with ICF	15

7 Indicative Project Plan	16

7.1 Scope of elaboration phase	16

7.2 Projection of overall project size and resource requirements	16

7.2.1 Expected project resource requirement	16

7.2.2 Expected project impact and benefit	16

7.2.3 Indicative resource estimates for elaboration, construction, transition and maintenance:	16

8 Appendices	17

8.1 Appendix One : Related user requests	17

# Glossary

## Domain Terms

| Functional status | Functional status is variously defined in the health field, by clinicians with different emphases as well as in different policy contexts. This NCVHS project uses a broad view of functional status that covers both the individual carrying out activities of daily living and the individual participating in life situations and society. These two broad areas include 1) basic physical and cognitive activities such as walking or reaching, focusing attention, and communicating, as well as the routine activities of daily living, including eating, bathing, dressing, transferring, and toileting; and 2) life situations such as school or play for children and, for adults, work outside the home or maintaining a household. |
| --- | --- |
| Functional abilities | Syn: Functional limitation; Functional capability Functional ability is the actual or potential capacity of an individual to perform the activities and tasks that can be normally expected. A given function integrates biological, psychological and social domains. It becomes increasingly important to measure the functional ability of an individual, especially related to long term care, because functional ability is a key factor in determining the individual's quality of life and it correlates to physical and mental health. |
| Activities of daily living | Activities of daily living (ADLs) are the most basic and fundamental functions of self-care, and they are used to describe the functional status or functional ability of a person, usually with reference to older people or people needing long-term care. There are several dimensions of ADLs and people are classified as independent or dependent on each of them. These functions are bathing, dressing, using the toilet, transferring in and out of beds or chairs, continence, and eating. |
| Instrumental activities of daily living | Instrumental activities of daily living are a subset of activities of daily living (ADLs). They include activities that are required to live independently, such as cooking and shopping. They are contrasted with basic activities of daily living (bADLs), which include basic self-care functions such as eating and bathing. |
| International Classification of Functioning, Disability and Health (ICF) | The International Classification of Functioning, Disability and Health, known more commonly as ICF, is a classification of health and health-related domains. These domains are classified from body, individual and societal perspectives by means of two lists: a list of body functions and structure, and a list of domains of activity and participation. Since an individual’s functioning and disability occurs in a context, the ICF also includes a list of environmental factors. |

# Introduction

## Purpose

The purpose of this project is to consider the concepts surrounding functional status and activities of daily living.

SNOMED CT projects transition from Inception Phase  Elaboration Phase  Construction Phase  Transition Phase. This document describes the Inception Phase. The elaboration phase, in which one or more technical solutions may be developed and tested, may result in more than one document.

The purpose of the Inception Phase is to agree with stakeholders the detail of the problem to be addressed and its scope boundaries.  The resulting problem description must also be of sufficient detail such that the size and impact of any resolution might have on the terminology as a whole and its users can be understood.

Subject to adequate review by stakeholders and subsequent revision, the inception phase document becomes the primary input to the Elaboration Phase of the project, in which the potential solutions are considered.

## Audience

The audience for this document includes all standards terminology leaders, implementers and users but is especially targeted at those stakeholders from the domain, including special cases.

### Identification of stakeholders

World Health Organization - The International Classification of Functioning, Disability and Health

IHTSDO Nursing Special Interest Group

IHTSDO Allied Health Professionals Special Interest Group

Canadian Health Outcomes for Better Information and Care (C-HOBIC)

College of Occupational Therapists (UK)

### Input from stakeholders

SNOMED CT has high proportion of content to support basic concepts of The International Classification of Functioning, Disability and Health (ICF) but has less content to support the degree of support/intervention/assistance required.  C-HOBIC demonstrates a structured approach that has been widely evaluated, not only in Canada but across the world.  C-HOBIC uses an amalgam of a number of existing methodologies to evaluate current status over time and/or the degree of intervention assessed to be required at each point.

Throughout the developed world failings in care are now dominating the press, whilst there have been huge improvements in medical/surgical treatments this has often left budgets for care itself being squeezed by increased demand and diminishing financial and human resource.  The improvements required in health care systems envisioned by the introduction of IT can only be achieved if business intelligence tools can identify those patients with needs for healthcare, the resource requirements of those people and those who have improved to a sufficient amount to scale down interventions and discharge from care.

Before a widespread consultation is undertaken to ensure content reflects current and future requirements appraisal and cleansing of existing content is essential.  Content appears to have been acquired from multiple sources with a greater priority being placed on authenticity of description that conceptual alignment with existing and similar content.

### Degree of consensus on the statement of problem

Informal feedback has suggested that the structured content in SNOMED CT requires some improvements to consistency and the ability to navigate these hierarchies, for example for subset development and analysis.  Incomplete subsuming due restricted modeling can result in incomplete or erroneous results, lexical results can be challenging with primitive search algorithms, e.g. the token “able” is within the token “unable” and “disabled”.  Additionally the level of granularity expressed in SNOMED CT has been widely expressed as inadequate to support recording of patient assessments and determining care needs and the level of resource that is required for safe care.

Many structured assessments use parts of this hierarch but are typically composite to a degree that would be considered unacceptable in the terminology.

# Statement of the problem or need

## Summary of problem or need, as reported

- In the area of functional assessment, an array of similar, but conceptually different ways of interpreting/recording assessment findings exist

- Unconstrained users may be challenged to understand the nuances between the various different patterns of concepts

- Coverage is incomplete with some functional states/needs elaborated to a greater extent than others.

- Incomplete modeling means identification of people with care needs and who conversely have recovered from historical dependence

- The granularity reflected in some schemes appear difficult to reflect conceptually in an intuitive way,  e.g. maximal assistance and total dependence

- Analysis challenging as modelling does not always include levels of dependence/abilities

### Typical current patterns in SNOMED CT

In the area of functional assessment, SNOMED CT reflects some of the array of similar, but conceptually different ways of interpreting/recording assessment findings.  It may be confusing in an unconstrained browser to understand the nuances between the various different patterns of concepts, which have developed over time to support multiple assessment tools focusing on independence/assistance/dependence or able/difficulty/impairment/unable/disability.

It has been widely disputed whether “does” and “does not” belong in this hierarchy at all as they are not really “abilities”.  Equally the dependence axis appears to be misplaced in this group of concepts

In many cases the content may be relatively easy to constrain to particular patterns of use by use of pre-configured forms/templates, the unrestrained use in a record may currently be difficult to report specific outcomes from unless a professional body of understanding to consider layers of equivalence between levels of need and levels of ability/disability emerges.

For this to be effective, a corresponding and unique layer is required along the lines of the following table.  Please note, the long-term quality improvement suggests that levels of dependence should perhaps be related to procedures rather than findings.

| Levels of dependence | Levels of ability | Levels of occurrence |
| --- | --- | --- |
| Independent | Able / Able to and does … | Does / Able to and does … |
| Assisted / Requires assistance | Difficulty |  |
| Assisted / Requires assistance | Impaired / Impairment |  |
| Dependent | Unable | Does not … |

The degree of modeling of concepts appears to have improved greatly in recent releases in the International Edition but many users of the terminology do not have access to anything but the lexical descriptions and in some cases the hierarchies of SNOMED CT.

Looking at the hierarchy above there are various apparent issues, e.g. The concept 224280009 | Special category of telephone user does not subsume

224282001 Blind telephone user

224283006 Deaf telephone user

224284000 Deaf-blind telephone user

224281008 Disabled telephone user

It also asserts that they are subsumed by 300736007 | Difficulty using telephone, whereas the reality may be very different, either because of education, device design or specific aids or adaptations which mean that they are able to use the telephone without issue.

### Typical representation in C-HOBIC

Extremes of ability and disability well catered for in both C-HOBIC and SNOMED CT, however currently C-HOBIC C has greater granularity for assistance need and ability in all areas.  The concepts of set-up help only and supervision do not consistently appear represented in SNOMED CT currently.  The number of layers of granularity reflected in C-HOBIC appears challenging to reflect conceptually in an intuitive way.  For example, there appears to be an effectively similarity between maximal assistance and total dependence.

There are a number of gaps for generic assessments in SNOMED CT and were there a need to make this specifically a C-HOBIC representation with scoring, no concepts currently exist to support this.  However, this would limit the usefulness to Canada (unless adopted by other countries) and therefore would probably belong in their national extension.  However the functional findings and observables are more generic in nature and should be represented in a more complete and consistent form in the International Edition of SNOMED CT.

| Levels of need | Levels of ability |
| --- | --- |
| Independent | Able |
| Pre-activity assistance | Able with pre-activity assistance |
| Supervision | Able with supervision |
| Limited assistance | Some difficulty |
| Extensive assistance | Moderate difficulty |
| Maximal assistance | Extreme difficulty |
| Dependent | Unable |

## Summary of requested solution

- Consult on splitting the abilities model to reflect abilities, dependence and activity

- Create navigational concepts to subsume concepts by the abilities model.

- Complete the modeling improvements to ensure that concepts are fully defined wherever possible.

- Enhance content to ensure all relevant axes are represented to a level that reflects the needs of clinical practice

- Update modeling and IsA relationships and de-duplicate concepts duplicated in functional and ADL hierarchies to ensure appropriate subsuming of concepts

## Statement of problem as understood

- ICF undergoing major revision

- C-HOBIC and similar tools are attempting to drive a better understanding of the needs of their populations and the impact of care

- ICNP problem list and others may need incorporation into SNOMED CT

- Failure of care is now overtaking medical negligence in terms of public visibility

- Healthcare organizations need better oversight of care needs and delivery to enable active management and prevention of unnecessary morbidity and mortality from care deficit

## Detailed analysis of reported problem, including background

UK concepts have been included in the analysis as most are (or should be) pending move to the International Edition of SNOMED CT.

| Concept grouping | Number of concepts (International and UK) |
| --- | --- |
| Able to | 670 |
| Optimum/optimal | 7 |
| Difficulty | 639 |
| Impaired | 149* |
| Unable to | 656 |
| Does | 551 |
| Does not | 606 |
| Independent | 57* |
| Needs assistance | 6 |
| Assisted | 131* |
| Dependent | 69* |

Not all relevant to this meaning

This analysis was undertaken using raw SQL lexical analysis using the UK preferred term description.  It is suggested that more comprehensive analysis may identify concepts which are equivalent but have alternative string patterns.

The vastly fewer numbers for the dependence type concepts suggest that this is a less common approach in other terminologies incorporated in SNOMED CT and/or there is less consistency of wording.  It is not suggested that levels of dependence are actively added to, but considered on a cases by case basis.  Specifically because this infers a degree of intervention may be required and thus procedure type concepts are probably a more appropriate way to reflect these e.g.

## Subsidiary and interrelated problems

ICF review

Observable review

LOINC harmonization agreement

Nursing problem list

# Risks / Benefits

### Risks of not addressing the problem

- Analysis of functional status and determination of care needs may continue to be challenging

- An additional vocabulary may be needed alongside SNOMED CT

- Use of the information model in an unstructured bespoke way per patient may make derivation of information for primary and secondary purposes challenging or effectively impossible.

- Subset membership may continue to be suboptimal due to inappropriate or incomplete subsuming of concepts

- Workload to identify care needs and dependence levels continues to be high or effectively unachievable

- Inconsistency of representation - each national release center will address their immediate needs diverging from a common approach that can be consistently mapped to ICF

- Difficulty transferring between differing models interpretation

### Risks of addressing the problem

Impact of workload to alternative projects

Potential disruption to existing queries (but this should improve their quality and reflect their intended membership better)

# Requirements: criteria for success and completion

## Criteria for success/completion

Activities of daily living/functional status concepts are fully modeled

Concepts are not duplicated in functional and ADL hierarchies

## Strategic and/or specific operational use cases

Outline fit with IHTSDO strategic goals;

Broaden the use of SNOMED CT, within and across health information systems, countries and professions

- Facilitate the accurate collection and sharing of clinical, public health, and related health information through improving the semantic representation and interoperability of health records (including personal health records and those created by health professionals).

- Contribute to improved delivery of care by the clinical and social care professions through supporting efficient, effective, and safe decision support

- Enable ‘health system’ or ‘secondary’ uses of data held in individuals’ health records.  The range of secondary uses includes, but is not limited to; links with classifications and other tools that support quality improvement activities at the health system level, clinical research, and activity reporting.

### Use case 1 – Falls prevention service care management

#### Fit with IHTSDO strategy

The use of functional status and activities of daily living are widespread outside the medical profession by clinical and non-clinical professions.  E.g. a falls prevention service

- Functional assessment by multidisciplinary team in relation to activities of daily living

- Physiotherapy in relation to mobility

- Occupational therapy in relation to assessment for functional aids

- Multidisciplinary case conference needing to identify and manage high risk clients.

### Use case – Long term condition care management

#### Fit with IHTSDO strategy

The use of functional status and activities of daily living are widespread outside the medical profession by clinical and non-clinical professions.  E.g. long-term conditions

- Functional assessment by multidisciplinary team in relation to activities of daily living

- Physiotherapy in relation to restoration of mobility e.g. following myocardial infarction

- Occupational therapy in relation to assessment for functional aids to cope with changing needs

- Speech and language therapy e.g. stroke rehabilitation

- Multidisciplinary case conference managing high risk patients and rehabilitation plan

# Outline Possible Technical Approaches and Concept Model

Explain what the problem solution is likely to entail

Will concept model change be needed?

Will terming guidance and rules be needed?

Capture and communicate concept model and terming rule options

Optionally: note candidate solutions that are immediately apparent; envision the concept model (‘architecture’), identify concept model goals, identify implementation impacts and requirements, and identify constraints on the projected concept model

Optionally: identify interfaces to information models, external coding systems, or other standards

## Indicative Solutions

### Approach One – create high level concepts and enhance modeling by adding IsA relationships

Create high level concepts for

- Able to perform activity of daily living

- Difficulty performing activity of daily living

- Impairment performing activity of daily living

- Unable to perform activity of daily living

- Independent performing activity of daily living

- Requires assistance with perform activity of daily living

- Dependent performing activity of daily living

And others identified in the analysis

Enhance modeling in largely technically delivered solution by modeling the high level concept and delivering improved modeling by inheritance of added IsA relationship.

#### End user Impact of approach one

Immediate improvement in identification of cohorts through inheritance

Fast delivery of improvements in single release cycle credible

Likely to be further changes to content due to modeling improvements and harmonization with ICF

### Approach Two – Detailed modeling of each concept to enhance quality

Create high level concepts for

- Able to perform activity of daily living

- Difficulty performing activity of daily living

- Impairment performing activity of daily living

- Unable to perform activity of daily living

- Independent performing activity of daily living

- Requires assistance with perform activity of daily living

- Dependent performing activity of daily living

And others identified in the analysis

Enhance modeling in largely terminologist delivered solution by modeling the concept appropriately either directly to high level concept or an intermediate concept delivering improved modeling by inheritance of additional relationships.

#### End user Impact of approach two

Improvement in identification of cohorts through inheritance and other modeling improvements

Delay in delivering this may be detrimental to immediate client and business needs

### Approach Three – Creation of new content and harmonization with ICF

Detailed analysis work alongside the harmonization agreement with ICF

Create high level concepts for

- Able to perform activity of daily living

- Difficulty performing activity of daily living

- Impairment performing activity of daily living

- Unable to perform activity of daily living

- Independent performing activity of daily living

- Requires assistance with perform activity of daily living

- Dependent performing activity of daily living

And others identified in the analysis

Enhance modeling in largely terminologist delivered solution by modeling the concept appropriately either directly to high level concept or an intermediate concept delivering improved modeling by inheritance of additional relationships.

Improve understanding of the hierarchy of abilities specifically the order of difficulty and impairment and whether intermediate values are required to support more granular classifications e.g. C-HOBIC with perhaps “severe impairment”, “minimal impairment”

MOST ABLE

Able

Difficulty

Impairment

Unable

LEAST ABLE

It should be considered alongside this whether the levels of need should be associated with the activity related concepts (i.e. procedures) rather than findings as they currently are.

#### End user Impact of approach three

Harmonization with ICF in single step

Improvement in identification of cohorts through inheritance and other modeling improvements

Significant delay in delivering this may be detrimental to immediate client and business needs

# Indicative Project Plan

Estimate project size; Forecast project velocity and duration

Evaluate risks; Establish costs and articulate value; Plan deployment; Outline project lifecycle

## Scope of elaboration phase

Optionally:

Skills required

Solution Specification (Elaboration)

Implementation

Outline of work packages

Preventing recurrence of problem

Analysis of active SNOMED CT content findings and observables to identify

- All patterns represented

- Inappropriately placed concepts

- Duplicate concepts

- The concepts identified for each cohort of super types

## Projection of overall project size and resource requirements

### Expected project resource requirement

The initial project resource requirement is classed as SMALL – less than 1 person year

Expected to be small (6.1.1) to medium (6.1.2) size project.  Recommendation is for 6.1.1 followed by 6.1.2 if resources allow.  6.1.3 is likely to occur over time anyway but not in timescales that are required to deliver patient and business needs effectively.

### Expected project impact and benefit

The project impact is HIGH – significant improvement to majority of patients and high profile given the current media spotlight of failures of care and perceived delays in delivering benefits from use of information technology in health.

### Indicative resource estimates for elaboration, construction, transition and maintenance:

Elaboration phase: 	1 person month effort, 3-6 months elapsed time

Construction and transition phase: 	100-200 new concepts to be authored

Maintenance phase:	500-1000 new ‘frequent usage’ concept requests in 1st 3 years

# Appendices

## Appendix One : Related user requests

http://www.ncvhs.hhs.gov/010617rp.pdf

http://www.springerreference.com/docs/html/chapterdbid/82577.html

http://www.springerreference.com/docs/html/chapterdbid/81395.html

http://www.springerreference.com/docs/html/chapterdbid/184456.html

http://www.who.int/classifications/icf/en

http://www2.cna-aiic.ca/c-hobic/about/default_e.aspx