Nursing SIG Minutes Dec. 17th 2013

Regrets;

Nick Hardiker

Amy Coenen

Tae Youn Kim

Attendees:

Susan Matney

Zac Whitewood-Moores

Kathryn Hannah

Roberta Severin

Connie Beaufort

Judy Warren

An Caseneuf

Christine Spisla

Rhonda Oakes

Declaration of interest - none

Minutes approval – Moved by Zac, seconded Judy

- CHOBIC Final Technical Report and next steps – Kathryn/Susan

  - Recommendations

    - SIG to request addition of new observable concepts as listed in 2.2.2 and new observable concepts where required from the findings table in Appendix B.

    - No new findings concepts to be requested until the review of SCT Functions and ADLs model is completed.

    - IHTSDO to consider Functions and ADLs content development project as matter of urgency.

    - SIG to consider next steps for this work in the light of the motion passed in Washington meeting that the maps to C-HOBIC be published as a Refset by the IHTSDO.

  - Final Report

    - Make final technical report version 1.0

    - Submit to Professional SIG and MB.

    - Susan will send report to Professional SIG today question who to send for management board

    - Upload to Professional SIG collab space

  - Content request process

    - New observable concepts

      - Content needs to be formatted entered into SIRS – Susan will format and Zac QA – Susan complete by Jan 10th

      - Request that content be created for July release

  - Observable C-HOBIC Refset (findings refset will be future)

    - Inception document for observable refset – will be drafted by Judy/Kathryn

      - Draft will be done by Judy and submitted as FYI to content.

      - Judy will report to content committee that the inception document is coming to them.

      - Nursing SIG to approve in Jan. meeting

  - Content modelling exercise CHOBIC observations to observables model (Kathryn, Susan and Judy). Report to Daniel Karlson

    - Susan to schedule meeting for modelling for early Jan.

Motion to approve technical report made by Zac and seconded by Judy.

- ADL/functional abilities area of SNOMED CT – Zac

  - Zac to forward to Professional SIG stating that other projects (C-HOBIC, Problem list, ICNP equivalency mapping) are being held up by this work.

    - May want to include international physical therapists www.wcpt.org

  - Could add the technical document as a hyperlink.

  - Send out discussion to Nursing SIG re escalating the project

    - Any comments to Zac by Christmas eve.

- ICNP equivalency mapping validation– Susan

  - Susan reviewed the recommendations sent to ICNP.

- Nursing Problem Subset Internationalization Plans– Susan/Judy/Amy

  - Will discuss next month when ICNP is on the call.

- Professional SIG Coordination Group  - First meeting report

  - Jane Millar overseeing coordination of SIGs

  - Prepare slide deck showing nursing SIG working

    - I will we can share.

- Content work items:

  - C-HOBIC observation requests

  - New nursing content into SNOMED CT based on missing ICNP mappings to SCT.

  - Nursing problem subset for international use

  - C-HOBIC subset

- Anne Casey – suggestions for a thank-you gift.

- AOB –

- Next meetings: 21 Jan 2014, 18 Feb 2014, 18 March 2014