Nursing SIG Minutes Jan. 21 2014

Regrets;

Kathryn Hannah

Rhonda Oakes

Attendees:

Susan Matney

Zac Whitewood-Moores

Sandra Ekimoto

Martha Badger

Amy Coenen

Nick Hardiker

Declaration of interest - none

December minutes approval – Zac motioned.

- C-HOBIC Final next steps – Kathryn/Susan

  - Actions

    - Submitted to MB and Professional SIG

    - Observable concepts as listed in 2.2.2 and new observable concepts where required from the findings table in Appendix B.

    - IHTSDO to consider Functions and ADLs content development project as matter of urgency.

    - SIG to consider next steps for this work in the light of the motion passed in Washington meeting that the maps to C-HOBIC be published as a Refset by the IHTSDO - Zac.

  - Content request process

    - New observable concepts

      - Content formatted entered into SIRS – done

      - Request that content be created for July release

  - Use in other countries

    - Ireland – need to follow-up with Kathryn

  - Observable C-HOBIC Refset (findings refset will be future)

    - Inception document for observable refset – will be drafted by Judy/Kathryn – Susan will follow-up with them.

      - Draft will be done by Judy and submitted as FYI to content.

      - Judy will report to content committee that the inception document is coming to them.

      - Nursing SIG to approve in Feb. Meeting?

  - Content modelling exercise CHOBIC observations to observables model (Kathryn, Susan and Judy). Report to Daniel Karlson

    - Susan to schedule meeting for modelling before Feb nursing SIG meeting.

- ADL/functional abilities area of SNOMED CT – Zac

- ICNP equivalency mapping table press release today– Susan/Nick

- ICNP/IHTSDO harmonization agreement – ICN and IHTSDO met

  - Meeting schedule for SIG and ICN leaders 2/6

- Nursing Problem Subset Internationalization Plans– Susan/Judy/Amy

  - Will discuss next month after meeting above.

- Review work items

- Anne Casey – suggestions for a thank-you gift - ?Florence Nightingale bear. Nick will investigate when it will be back in stock.

- AOB –none

- Next meetings: (always the third Tuesday of the month at 1700 UTC.

18 Feb 2014

18 March 2014

15 April 1014