Process for managing content development projects to be submitted to the International Release by Healthcare Professional Groups - draft

This draft document describes the steps by which Healthcare Professional Working Groups recognised by the IHTSDO can develop and submit content changes and developments to the International Release of SNOMED CT. Coordination will happen through the Healthcare Professional Coordination Group (HCPCG) to ensure that there is communication between professional groups on any development and engagement of relevant healthcare professionals.

This process will be followed for specific content development areas and does not apply to individual requests for small changes – i.e. this applies where there is significant redesign or large numbers of grouped/linked requests which may in some cases require a project. The benefits to this approach are to provide transparency about activity and a clear path for Professional SIGs to progress development work and have it identified in the IHTSDO work plans.

Identifying and documenting development area:

An IHTSDO Professional SIG or the Healthcare Professional Coordination Group itself will identify an area for development. This should be documented using a ‘Proposed content development area’ template, including the following key items:

- Use case (s)

- Scope and purpose

- Required timelines

- Healthcare professional groups involved

- Resources available to help the work

- Priority (from professional perspective)

- Estimated size of project (from professional perspective) – small, medium, large

- References

Note that the information required will be in a template such that it can be readily transferred to an Inception template, should the proposed work item be agreed.

Confirming professional input and any overlap with other work within Professional SIGs

The proposed work item will be shared and discussed by the Healthcare Professionals Coordination Group (HCPCG) for feedback and identification of any overlap with any work in Professional SIGs and recommend any additional professional input that is required – it will then be the role of the HCPCG to advise on how such resources may be sourced.

Gaining feedback and agreement to proceed on Content Development Process

With the support of the HCPCG, the ‘Proposed content development area’ template will be submitted to the Head of Content Development for review of request including overlap with existing work items (either scheduled or pending), timelines and priorities, resources required etc.

The decision on how to progress will be made by the Head of Content Development, in consultation with the SIG and the content authoring team, as to whether this is a project or whether changes can be submitted through the IHTSDO request submission tool (SIRS)by the Professional SIG. If the work is considered significant enough to be a project, it will be presented to the IHTSDO Content Committee with recommendations on the prioritisation of the work and any necessary resources required.

Next steps after consideration by Content Committee – Project Plan and Inception Phase

If there is agreement to progress, an editor (IHTSDO or Consultant Terminologist) will be appointed to work with the Professional SIG in moving the work forward – normally the named editor for the SIG, but in some cases it may be different depending on any specific knowledge required. The SIG will work with the editor to put together a project plan which will be reviewed and signed off by the Head of Content Development and then progress to developing the Inception Phase. During the Inception phase the SIG will be asked to be actively involved in obtaining stakeholder feedback.

When the Inception Phase document is drafted, it will be reviewed by the HCPCG and then submitted to the Head of Content Development for review and sign off to progress to Elaboration Phase – based on the agreed project plan.

Elaboration Phase

The SIG will normally develop the Elaboration Phase of the project, with key input from the responsible editor to ensure that any proposed solutions meet with all aspects of editing guidance. The editor will act as liaison with the Content Development team to seek advice as required. The HCPCG will provide any clinical oversight advice if it is needed. Note that during Elaboration Phase new information may be uncovered that requires updates of previous documents, timelines and project plans.

The Elaboration Phase document must include details of stakeholder engagement and also an impact assessment of the proposed changes. The document, when completed, will be reviewed by the HCPCG and handed over to the Head of Content Development for review and sign off to ensure all the documentation is complete. The proposed development will continue to Construction phase based on the project plan.  The SIG may be asked to advise where a number of potential solutions are documented. Note that the approach proposed in the Elaboration phase may change as part of construction activity. This may include the authoring/implementation of the proposed change, and also may include consultation with the Content Committee

Construction Phase

The responsible professional SIG will provide professional advice as required to the IHTSDO Editor(s) during Construction Phase. As identified above, the proposed solution set out in the Elaboration phase may require amendment as editing progresses. This will be shared with the SIG. Feedback will be required in a timely manner to reduce delays to the availability of the content.

Review of content development

If ‘Review’ is part of the project plan, the SIG, and in some cases the HCPCG, will have a chance to review the relevant new/changed content prior to release as a SNOMED CT Beta version. IHTSDO will provide tools and/or format to do this. There should be agreed criteria for such a review based on the use case of the work.