## Map Leads
Personnel Identifier | Hours to date | Tasks
ML-1 | 160 | Batch management, conflict reviews, JAG meeting, Comparator requests , team meetings, Leadership meeting following IHTSDO GA
ML-2 | 105 | Batch mangement and team meetings, revision advice to MS
265

## Map Specialists
Personnel Identifier |  | MS-1 |  | MS-2 |  | MS-3 |  | MS-4 |  | MS-5 |  | MS-6 | Summary
May 2011 | 6
Batches Processed |  | 126 |  | 107 |  | 21 |  | 46 |  | 28 |  | 34
Mapping Hours |  | 397.5 |  | 336.75 |  | 104.25 |  | 107.5 |  | 62.25 |  | 108.5
Other Hours |  | 15.25 |  | 13 |  | 13.75 |  | 8 |  | 3.5 |  | 3.5
Total Hours | 412.75 |  | 349.75 |  | 118 |  | 115.5 |  | 65.75 |  | 112 |  | 1173.75
Total Maps |  | 2828 |  | 2007 |  | 500 |  | 1126 |  | 451 |  | 695 | 7607
Avg Maps per Hour | 6.8516 |  | 5.7384 |  | 4.2373 |  | 9.7489 |  | 6.8593 |  | 6.2054 |  | 6.4809
Data collection began on 12 March 2011 and is updated each week on Wednesday - This report is for May 14 to May 20, 2011. Late report posted 30 May 2011.
This data is derived from time sheets completed by map specialists. It is important to understand that total maps in this situation includes duplicate maps since two specialists process the same concept for comparison - only one map per SNOMED CT concept is published. We track this production to evaluate the time spent per map record processed to assess the average number of maps per worked hour.
Note on K1: Rita Scichilone: No report this week (vacation)
Note on B2: Rita Scichilone: Week beginning with date indicated. Weeks start on Saturday and end on Sunday.
Note on A3: Rita Scichilone: Count of individual batches worked on in the reporting period - overlaps possible if the same batch is worked on in two reporting periods.
Note on A4: Rita Scichilone: Time spent on mapping.
Note on A5: Rita Scichilone: Team meetings, technical problem troubleshooting, etc.
Note on B6: Rita Scichilone: Total hours of work
Note on D6: Rita Scichilone: Total hours of work
Note on F6: Rita Scichilone: Total hours of work
Note on H6: Rita Scichilone: Total hours of work
Note on J6: Rita Scichilone: Total hours of work
Note on L6: Rita Scichilone: Total hours of work

## Consensus Panel
Personnel Identifier | Hours | Tasks
CP-1
CP-2
CP-3

## Other Contributing Personnel
Personnel Identifier | Hours | Tasks
TC-1 | 54 | Data compilation, MapSig calls, Map Tooling,
LR- 1
LR-2
ML-1 | 179 | Batch assignments, map lead supervision, coordination, troubleshooting
ML-2 | 112.5 | Batch assignments, map lead supervision, coordination, troubleshooting

## Graphs
ToDate
March | 2172
April | 5354
May | 7607
June
July