DRAFT MEETING MINUTES

| Meeting date:September 12,2011 |  |  | Group: Mapping SIG |  |
| --- | --- | --- | --- | --- |
| Meeting time: 20:00-21:00 UTC |  |  |  |  |
| Attendees: Ginette Therriault (GT), Jim Campbell (JRC) , Candy Hall (CH), Georg Brox(GB), Pat Wilson(PW), Kathy Giannangelo(KG) David Bergland (DB), Brenda Henley(BH), Kin Wah Fung(KWF), Hazel Brear(HB), Roberta cardiff(RC) |  |  |  |  |

Regrets: Rita Scichilone

| Time for next meeting: September 26, 2011 |  |  | Place for next meeting: GoToMeeting and Teleconference |  |
| --- | --- | --- | --- | --- |

| ## Agenda item | ## Discussion | ## Decision | ## Action |
| --- | --- | --- | --- |
| Review of minutes from August 22, 2011 | Minutes were reviewed and approved as written. |  | Confirmed minutes to Collabnet |
| ICD-10 phase 1 mapping project | Due to content validation work, RS was not available to present mapping statistics. HB and GT reported most source concepts have been assigned to map specialists. Map productivity spreadsheet was reviewed. JRC reported that content validation work to begin shortly. JRC reviewed preview publication materials distributed to MapSIG and discussed release materials. Discussion: how to elicit response to preview publication? Member forum has been polled. | Preview publication forwarded to SIG members MapSIG to forward query to national release centers soliciting feedback | JRC to forward request through quality officer |
| ICD-10 map phase 2 planning | JRC, KWF reported three themes under development for phase 2: - SNOMED maintenance to bring map up to date with SNCT July 2012. Criteria under development - New content mapping within stated scope (30K concepts) - Workbench migration for map tooling |  | Report on project development each meeting |
| Sydney meeting planning | KG,GT,HB: report two posters for presentation: experiences with tooling and observations on mapping KWF presented the draft conference schedule received from IHTSDO. Final times and room assignments yet to be issued |  | Updated schedule to be distributed to MapSIG as available. Concurrent meetings with ICNP and ICPC to be pursued. |
| ICD-10-CM mapping project | KWF provided brief report of ICD-10-CM mapping activities. GB: Query regarding availability of classification and map results to affiliates: Czech Repuglic, Estonia, Lithuania, Italy? | DB reported that NCHS had not yet issued guidelines |  |
| Next Conference CallSeptember 26; 2000UTC |  |  | KWF to organize and chair |