DRAFT MEETING MINUTES

| Meeting date:September 26,2011 |  |  |  |  | Group: Mapping SIG |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Meeting time: 20:00-21:00 UTC |  |  |  |  |  |  |  |  |
| Attendees: Jim Campbell (JRC), Georg Brox(GB), Pat Wilson(PW), Kathy Giannangelo(KG) David Bergland (DB), Brenda Henley(BH), Kin Wah Fung(KWF), Hazel Brear(HB), Roberta cardiff(RC), Julia Xu (JX), Ginette Therriault (GT), Rita Scichilone (RS), Jane Millar (JM), Karen Coghlan (KC) |  |  |  |  |  |  |  |  |
| Time for next meeting: October 12, 2011in Sydney |  |  |  |  |  | Place for next meeting: GoToMeeting and Teleconference |  |  |  |

| ## Agenda item | ## Discussion | ## Decision | ## Action |
| --- | --- | --- | --- |
| Review of minutes from Sept 12, 2011 | Minutes were reviewed and approved as written. |  | Confirmed minutes to Collabnet |
| ICD-10 phase 1 mapping project | Discrepancies noticed between map statistics prepared by NLM and map lead spread sheets. RS will generate work throughput statistics. JRC and RS reported that content validation work was going well. There was a meeting among the validators to discuss discordance records. Maps will be sent to statistician by Sept 30. There will be an organization meeting about the results in first week of October. Some preliminary findings will be discussed in Sydney. To elicit response to preview publication - Member forum has been polled. |  | Map leads to send latest worksheets and NLM will look at the repository and do batch-level and concept-level reconciliation of counts. JM will remind member forum representative to gather feedback |
| Sydney meeting planning | KWF presented draft agenda for MapSIG/PG meeting on 10/12. Group discussed content and assigned lead for each section. Joint meeting with FP/GP SIG from 11-12 noon. Joint meeting with Nursing will not be pursued. Two educational sessions on 10/13. Presenters assigned for each sub-section. Two posters on the mapping project will be presented by HB, GT and KG. Schedule has not been fixed. |  | KWF to send out final agenda to group |
| ICD-10 map phase 2 planning | JM briefed group on the document submitted to Management Board - Strive for fully-funded project - Phase 2 will cover maintenance of existing maps and mapping of remaining 90,000 concepts - Preferred option of mapping remaining concepts in 3 years |  | Feedback from Management Board expected on 10/10. JM will discuss with project leads afterwards. |
| Next Meeting October12 in Sydney; 22:30UTC |  |  |  |