## Mapping SIG Action Log
Action No. | Meeting Raised | Status | Action Owner (initials) | Title / Brief Description of Action Required | Due date | Progress | Closed date
1 | 2014-07-21 | Closed | KG | Post the QA reports that are released to the QA Committee to the Mapping SIG Collabnet site for member review. | 2014-08-11 | 11-Aug-2014: Posted 04-Aug-2014. Recommend close action. | 2014-08-11
2 | 2014-07-21 | Closed | HB | Place review of the report on the October face to face meeting | 2014-08-11 | 11-Aug-2014: Placed on draft agenda. Recommend close action. | 2014-08-11
4 | 2014-07-21 | Closed | HB | Forward potential face-to-face agenda items to Krista and Jim for collation and discussion at August meeting. | 2014-08-11 | 11-Aug-2014: Items forwarded and on todays agenda. Recommend close action. | 2014-08-11
3 | 2014-07-21 | Closed | MF | To share results of the IHTSDO 'Customer Engagement' Members survey when these are available. | Ongoing | 11-Aug-2014: The survey is owned by the MF. Once MF decides on action it may be possible to share the survey detail with Mapping SIG. Leave action open. 08-Sep-2014: Ongoing 09-Mar-2015: IG has the report but is unsure if he can share today. Will report back to group in April meeting. 13-Apr-2015: IG presented quite an extensive verbal report to the group. Close action. | 2015-04-13
5 | 2014-08-11 | Closed | JRC | Joint group (Implementation SIG, Events and Episodes PG) to clarify position on communication and collaboration. | TBA | 08-Sep-2014: Advice is to continue to 'talk'. Possibly work up a proposal for consideration in a future work plan. Continue with planned sessions at face to face meeting. Close action | 2014-09-08
6 | 2014-08-11 | Closed | KWF | Email a short summary of the US mapping activity for inclusion in the report to the Content Committee. | 2014-08-13 | 12-Aug-2014: Action complete. | 2014-09-08
7 | 2014-08-11 | Closed | KG | Post principles mentioned in the Quality Assurance and Metrics report. | 2014-09-08 | 08-Sep-2014: Action completed. Close action | 2014-09-08
8 | 2014-08-11 | Closed | KG | Provide a summary (for information only) of the number and types of issues that have been raised from the Open Tooling Framework. | 2014-09-08 | 08-Sep-2014: MST have not received any feedback at this time. Close action. | 2014-09-08
9 | 2014-08-11 | Closed | JRC/HB | Allocate 90 minutes on face to face agenda for Mapping tool demo. | 2014-09-08 | 08-Sep-2014: Action completed | 2014-09-08
10 | 2014-08-11 | Closed | All | Members of Mapping SIG to forward via email suggestions for agenda items. | 2014-09-08 | 08-Sep-2014: Suggestions received from one member. Discussed and agreed at the meeting. Close action | 2014-09-08
11 | 2014-09-08 | Closed | IG | Organise a demonstration of the new SNOMED CT Browser during the face to face meeting sessions. | 2014-10-11 | 27/10/2014: Demonstration delivered by Farzaneh and Suzanne | 2014-10-27
12 | 2014-09-08 | Closed | IG | Arrange for an update on the joint work between IHTSDO and LOINC. | 2014-10-11 | 27/10/2014: Demonstration delivered by Farzaneh and Suzanne | 2014-10-27
13 | 2014-09-08 | Closed | JRC/HB | Post draft agenda for face to face meeting. | 2014-09-09 | 09-Sep-2014: Action completed | 2014-09-09
14 | 2014-09-08 | Closed | JRC/HB | Finalise agenda and post 2 weeks prior to meeting | 2014-10-13 | 27-Oct-2014: Three versions of agenda posted | 2014-10-27
14 | 2014-10-27 | Closed | FA | To find out if the contract for the joint work is available for review | 2014-11-10 | 07-Nov-2014: The contract is not available for review and the contract work has been completed in the form of two reports which are available. The contractor is Mireia Rodriguez Naque of BITAC. Action completed | 2014-11-10
15 | 2014-10-27 | Closed | FA | Determine whether there is an update schedule for the SNOMED CT Browser | 2014-12-08 | 07-Nov-2014: Still checking with Rory about this item. 12-Jan-2015: Covered by RD at the January 2015 meeting. Close action. | 2015-01-12
16 | 2014-10-27 | Closed | JRC/HB | Add discussion of workplan to next meeting agenda | 2014-11-07 | 07-Nov-2014: Action completed | 2014-11-07
17 | 2014-10-27 | Closed | KL | Share Mapping Personnel Handbook with CH | 2014-11-10 | 10-Nov-2014: Action completed | 2014-11-10
18 | 2014-10-27 | Closed | JRC/HB | Add QA presentations from NLM and UK to next Mapping SIG meeting agenda | 2014-11-07 | 07-Nov-2014: Action completed | 2014-11-07
19 | 2014-10-27 | Closed | RD | Deliver a report on tooling developments at the January meeting | 2015-01-12 | 12-Jan-2015: Tooling report deliverd at the January meeting. Close action. | 2015-01-12
20 | 2014-10-27 | Closed | JRC/BK | Continue to chair joint work in developing a draft implementation guide for allergy/adverse sensitiities: See minutes 27-Oct-2014 for decisions and assignments. | Ongoing | 10-Nov-2014: Suggested continue and prioritised for 2015 workplan. Refelceted in action 23. Close this action | 2014-11-10
21 | 2014-11-10 | Closed | JRC/HB | Ensure MST report is high on December agenda as this has been deferred for last 2 meetings | 2014-12-08 |  | 2014-12-08
22 | 2014-11-10 | Closed | GB | Forward the meeting information for the next ImplementationSIG meeting | 2014-11-11 | 11-Nov-2014: Meeting details for 13-Nov-2014 at 14:00 UTC sent to JRC who has circulated. Action completed. | 2014-11-11
23 | 2014-11-10 | Open | JRC/KWF | Adverse sensitivity Implementation Guide (workplan #2) | Ongoing | 08-Dec-2014: Next call 09-Dec-2014 with ImpSIG 12-Jan-2015: Joint calls twice a month. All are invited to attend. Added to agenda as a standing item. 09-Mar-2015: The latest version is on collabnet although JRC is unable to locate at this time. JRC will locate and send group members a link. 13-Apr-2015: JRC has sent out a link via email, perhaps it failed. Sent link just before this meeting to HB HB will add to front page of MapSIG area on CollabNet and email to all those on the call.
24 | 2014-11-10 | Open (on hold) | All | Enhanced tooling (workplan #4) | Ongoing | 08-Dec-2014: Preliminary discussion and Communication to MF chair 12-Jan-2015: As there are a number of projects underway using IHTSDO tooling this item will be put on hold and revisited at a later meeting.
25 | 2014-11-10 | Open | HB | Quality Assurance activities (workplan #6) | Ongoing | 10-Nov-2014: Add first topic 'Rationale for selection of ICD-10 .8 Other specified and .9 Unspecified, to agenda and prepare discussion points with MST 08-Dec-2014: To add to February agenda 12-Jan-2015: First topic (.8 & .9 ) is on February agenda 09-Mar-2015: Next topic (Mapping of Syndromes & Rare Diseases - The role of Orphanet) is for discussion at the April meeting. 13-Apr-2015: Due to work priorities this has been postponed until May. We are circulating a list of difficult to map concepts and ask the group to map to inform the discussion in May.
26 | 2014-12-08 | Closed | BH | Review of browser support planned for ICD-10 map releases with MST |  |  | 2015-12-08
27 | 2014-12-08 | Closed | JRC | All calls of MapSIG will be recorded and posted to Collabnet |  | 08-Dec-2015: Decision of group today - chair will record and post. | 2015-12-08
28 | 2015-02-09 | Closed | HB | Reach out to members to volunteer to take notes at March 2015 meeting. |  | 09-Mar-2015:
29 | 2015-02-09 | Open | IG | Follow up with MF to see if results of Customer engagement survey are ready to be shared with SIG. | 2015-03-09 | 09-Mar-2015: No update for this meeting. Will check if this can be shared for next meeting 13-Apr-2015:
30 | 2015-02-09 | Closed | HB | Upload slides of quality assurance discussion (.8 & .9) to CollabNet. Upload a summary of the discussion and outcome for use by interested parties. |  | 09-Mar-2015: Action completed. Close | 2015-03-09
31 | 2015-02-09 | Closed | All | Members to forward suggested quality assurance topics for future meetings to HB. | 2015-03-09 | 09-Mar-2015: One topic received 'Mapping of Syndromes and Rare Diseases - The Role of Orphanet'. | 2015-03-09
32 | 2015-02-09 | Closed | JRC | Post meeting notice for joint work item (allergy/adverse sensitivity) on CollabNet. |  | 09-Mar-2015: Action completed. Close | 2015-03-09
33 | 2015-02-09 | Open | All | Forward examples of implementation guidance to DM at dmo@ihtsdo.org | 2015-03-09 | 09-Mar-2015: HB to check with Donna if she received any examples. 13-Apr-2015: No guidance sent to DM so far.NI reports that the guidance will follow the use case but the MST would like to have feedback on the level of detail required in guidance. KWF has some implementation guidance which may be useful. He will send to DM.
34 | 2015-04-13 | Open | HB | Email 7 concepts to group and post concepts on CollabNet area asking for feedback before the May meeting. | 2015-05-11
35 | 2015-04-13 | Open | All | Map the 7 concepts posted and send to HB at hazel.brear@hscic.gov.uk before the May meeting.

## Draft Workplan
Draft Workplan
Item.No. | Suggested items | Priority for 2015?
1 | Guidance on QA for users to require of vendors who support maps
2 | Adverse sensitivity implementation guide and refsets | Yes
3 | Observables implementation guidance; review and enhancement
4 | Enhanced tooling and support for NRC's | Yes
5 | Implementation Guide: Clinical fidings vs. Observables [aka "Domain integrity"]
6 | QA activity topics as they arise (starter topic is ICD-10 .8 & .9 differences) | Yes
7 | Mapping of a refset of the most common procedures