Map SIG

October 2012

SUBJECT

Risk and Issues Management for Mapping

PURPOSE

This paper outlines the IHTSDO approach to Risk and Issues Management and requests Members of the   Map SIG’s share their relevant experience of Risk and Issues Management when undertaking mapping work.

COMMENT

A. Background

As outlined in IHTSDO’s Risk and Issue Management Policy, IHTSDO aim to have a consistent and standardised approach to the identification, reporting and effective control of risk and issues to ensure that they are eliminated or reduced to an acceptable level.

Risk and issues are inherent in everything that IHTSDO does, and therefore good risk and issue management awareness and practice is a critical requirement for IHTSDO to have in place.

IHTSDO’s Risk and Issue Management Policy states that IHTSDO should identify, manage and mitigate risk and issues in order to reduce the likelihood of adverse incidents by proactively managing risk and issue.  There are four stages in the Risk and Issue Management Process:

- Identify

- Assess

- Address

- Review and Report.

B. Next steps

In the identification stage of the Risk and Issue Management Process, the Mapping Service aims to capture those risks and issues that will have a material impact on the delivery of activities and objectives.  In the process of identifying the risks and issues, the Mapping Service aim to:

- Establish what the risks and issues are

- Categorise the risks and issues

- Identify who owns the risks and issues

- Record the risks and issues on the risk and issue register

As the Map SIG brings their extensive experiences from their own organisations, the Mapping Service asks that they contribute their experience of  the identification of risks associated with mapping at all levels – e.g. tooling, processes, validation, delivery against timelines, training materials etc.  The Map Leads within the Mapping Service would then be able to build on this experience,  in order to identify and manage relevant risks and issues, using the IHTSDO mechanisms.

RECOMMENDATIONS

It is recommended that the Map SIG:

- Note the need for the identification of risk and issues in relation to mapping activities.

- Share experience of  identifying risks and issues associated with mapping, tooling, education materials etc.

Donna Morgan

12-Oct-2012