MEETING MINUTES

| Meeting date: Monday 22 October 2012 |  |  | Group: Mapping Special Iinterest Group (MapSIG) |  |
| --- | --- | --- | --- | --- |
| Meeting time: 0700-1500 UTC |  |  | Meeting place: Stockholm, Sweden |  |
| Attendees: See separate attendee list |  |  |  |  |

| Date for next meeting: Time for next meeting: |  |  | Place for next meeting: Teleconference |  |
| --- | --- | --- | --- | --- |

| ## Agenda item | ## Discussion | ## Decision | ## Action |
| --- | --- | --- | --- |
| Welcome | Review of Minutes of last meeting | Minutes approved. | Post final approved minutes |
| Future role of Map SIG | Since Phase 1 is finished, changes in the role of SIGs were reviewed. The proposed scope and responsibilities within IHTSDO was discussed. SIGs have been split into professional SIGs and functional SIGs. The MappingSIG is a Functional Special Interest Group and the Nursing SIG is an example of a Professional SIG. | MapSIG currently reports through the Technical Committee; however, the Senior Responsible Officer is Jane Millar. Ian Green explained the changes within the IHTSDO and gave reasons for reviewing the context of SIGs to clarify the roles in governance. There are moves to bring SNOMED editing in-house. The work plan is driven by member requirements. There was also demand for IHTSDO to make the procedure of work prioritization more transparent. | The MapSIG will provide expertise, advice and guidance in core functional areas for activities which link or associate SNOMED CT and other terminologies and classifications. The MapSIG will ensure an international focus which is not specialty-specific, and must identify past experiences to inform all activities. |
| Terms of Reference | The Mapping SIG updated their Terms of Reference (TOR) using a new template which provides guidance from the IHTSDO. The October 2007 MapSIG meeting record was reviewed as a starting point of discussion. | Kin Wah Fung presented some points he had drafted to prime discussion. Many attendees offered comments/suggestionsto the statements. Group agreed on a draft TOR which will be circulated to SIG Members and the Senior Responsible Officer for comment | Circulate the draft TOR to MapSIG Members and the senior responsible Officer for comment. (KWF) |
| Report from other mapping work in IHTSDO and internationally | ICPC map and GP/FP RefSet document was reviewed. UK NHS Map to ICD-10 (Hazel Brear) Canada shared their experiences with mapping work with ICD-10-CA (Ginette Therriault). ICD-10-CM map (Kin Wah Fung). | GP/FP RefSet and map itself will be released together, probably sometime in mid 2013 Slides reviewed looked at Development and Maintenance of UK NHS maps. They are up-to-date with current versions. Hazel will be carrying out a comparison between the IHTSDO MAPS and the existing UK NHS maps for the same concepts. Initially the comparison will be between the IHTSDO ‘TRUE or ‘ELSE target and the UK ‘DEFAULT’ target. Findings will be fed back to the Mapping Service and it was agreed that it would be useful to also feedback findings to the MapSIG group. RefSets were developed by Canadian Infoway included “Reason for Visits” and “Health Concern”. They will be mapped to ICD-9-CM and ICD-10-CA, which may be ready by next year. The tools and map of ICD-10 was heavily reused in the ICD-10-CM map due to the similarities between ICD-10 and ICD-10-CM. There were some changes in methodology because of the much more granular codes in some areas such as episode of care, laterality, trimester, affected fetus. A demonstration of the I-MAGIC (Interactive Map-Assisted Generation of ICD Codes) tool was given. This tool was originally developed for the ICD-10-CM map, but has been adopted to showcase the ICD-10 map as well. | Hazel will present the findings of this analysis at a future MapSIG meeting (HB) |
| Mapping from existing data to SNOMED CT ...I&I Subgroup | Beverly Knight explained the background of this new project to develop guidance for mapping existing data to SNOMED CT | Liaison with MapSIG would be beneficial | The MapSIG would like explanation of this document, especially the scope. Pending further details, Georg Brox, Hazel Brear & Kin Wah Fung expressed interest in participating in this work. |
| Report from Mapping Service Team - 2012 Work Plan status report - Briefing paper: Map SIG’s Role in Consensus Mgmt - Briefing paper: Risk Mgmt - Help desk management | The Mapping Service team (MST) introduced themselves. Kathy Giannangelo gave the history of the Mapping Service Team and the current status. In Phase 1, the consensus panel meetings took place at the end of the project, which was not ideal particularly as the decisions may affect ongoing mapping work. It was proposed that more frequent consensus panel meetings will be desirable. David Berglund, Kin Wah Fung, and Harold Solbrig are the current consensus panelists. Donna Morgan showcased the Mapping Service Personnel Handbook. Members shared their experience in how they support their users through a help desk or similar service | Current versions of SNOMED CT and ICD-10 will be used to update the Technology preview map. First baseline map will be released with the January 2013 release of SNOMED CT. Another training session for map specialists is planned for May 2013 to be hosted by UKTC. Experiences were shared on consensus mgmt in different countries. A new process was proposed and agreed. This will utilize the MapSIG membership as an advisory body with the MapSIG Chair or Vice-chair acting as consensus facilitator. In future, consensus panel meetings will take place during the regular SIG meetings Consensus Panel will appear as a regular item on the MapSIG agenda although this may not always need to be utilized. The new process should be discussed at the next meeting of the IHTSDO/WHO Joint Advisory Group (JAG). | The Mapping Service Team will notify the Map SIG and panelists beforehand about the consensus issues to discuss. (MST) To cater for scheduling conflicts, each panelist will have an alternative in case they cannot attend a specific meeting. (DB, HS, KWF) The MapSIG Chair or Vice chair will act as the consensus facilitator. (KWF) Add ‘Consensus Panel’ to MapSIG agenda as a regular item. (KWF) Add new Consensus Panel arrangements to the December 2012 JAG agenda for information. (JM) |
| Next meeting |  |  |  |