MEETING MINUTES

| Meeting date: April 4, 2011 |  |  | Group: Mapping SIG |  |
| --- | --- | --- | --- | --- |
| Meeting time: 2000 UTC |  |  |  |  |
| Attendees: Jim Campbell (JRC), Kin Wah Fung (KWF) (chair), Rita Scichilone(RS), Brenda Henley(BH), Julia Xu(JX), Ginette Therriault(GT), David Berglund(DB), Pat Wilson (PW), Monique Stark (MS), Kathy Farndon (KF), Hazel Brear (HB), Karen Coghlan (KC), Roberta Cardiff (RC) |  |  |  |  |

| Time for next meeting :April 18, 2000UTC HB to chair |  |  |  |  |
| --- | --- | --- | --- | --- |

| ## Topic | ## Discussion | ## Decision | ## Action |
| --- | --- | --- | --- |
| Minutes review 3/21/2011 | No amendments |  | Accepted as official minutes |
| ICD-10 Map Quality Assurance | RS has discussed with AHIMA and will put together a proposal. WHOFIC also informed of the QA plan. Some potential manpower (a physician) from Thailand. KWF- NLM has no spare resources at this point for QA DB – no spare resources at NCHS GT – received some information for possible sources of SNOMED coded records, will follow up |  | JRC to contact UK / AU / CA national release centers for interest as external review agency *Source records: GT to contact Francis Lau re/SNOMED record resource; JRC to contact UK and KP *Usage validators: Kristina Perssons to contact Member Forum regarding volunteers for validation sites (confirmed at IHTSDO April meeting) |
| Progress of Map Project Phase I | Third week of mapping since new map specialists joined RS – generating statistics HB & GT – map leads are trying to resolve conflicts as much as possible, many are simple ones like map advice and self vs self and descendant axis Assignment of batches is time-consuming as the subversion repository is slow in response time Comparator is working OK Should also keep track of hours put in by map leads for statistics |  | Team meeting coming Wednesday |
| Review of first 500 maps | KWF – many high level concepts (with 30 or more descendants) missing ‘ADDITIONAL CODES NOT MAPPED’ advice. Should they be added automatically? |  | HB to review list. Will discuss again next call |
| Next Conference Call |  |  | April 18; 2000UTC |