## Mapping SIG Action Log
Action No. | Meeting Raised | Status | Action Owner (initials) | Title / Brief Description of Action Required | Due date | Progress | Closed date
1 | 2014-07-21 | Closed | KG | Post the QA reports that are released to the QA Committee to the Mapping SIG Collabnet site for member review. | 2014-08-11 | 11-Aug-2014: Posted 04-Aug-2014. Recommend close action. | 2014-08-11
2 | 2014-07-21 | Closed | HB | Place review of the report on the October face to face meeting | 2014-08-11 | 11-Aug-2014: Placed on draft agenda. Recommend close action. | 2014-08-11
4 | 2014-07-21 | Closed | HB | Forward potential face-to-face agenda items to Krista and Jim for collation and discussion at August meeting. | 2014-08-11 | 11-Aug-2014: Items forwarded and on todays agenda. Recommend close action. | 2014-08-11
3 | 2014-07-21 | Open | MF | To share results of the IHTSDO 'Customer Engagement' Members survey when these are available. | TBA | 11-Aug-2014: The survey is owned by the MF. Once MF decides on action it may be possible to share the survey detail with Mapping SIG. Leave action open. 08-Sep-2014: Ongoing
5 | 2014-08-11 | Closed | JRC | Joint group (Implementation SIG, Events and Episodes PG) to clarify position on communication and collaboration. | TBA | 08-Sep-2014: Advice is to continue to 'talk'. Possibly work up a proposal for consideration in a future work plan. Continue with planned sessions at face to face meeting. Close action | 2014-09-08
6 | 2014-08-11 | Closed | KWF | Email a short summary of the US mapping activity for inclusion in the report to the Content Committee. | 2014-08-13 | 12-Aug-2014: Action complete. | 2014-09-08
7 | 2014-08-11 | Closed | KG | Post principles mentioned in the Quality Assurance and Metrics report. | 2014-09-08 | 08-Sep-2014: Action completed. Close action | 2014-09-08
8 | 2014-08-11 | Closed | KG | Provide a summary (for information only) of the number and types of issues that have been raised from the Open Tooling Framework. | 2014-09-08 | 08-Sep-2014: MST have not received any feedback at this time. Close action. | 2014-09-08
9 | 2014-08-11 | Closed | JRC/HB | Allocate 90 minutes on face to face agenda for Mapping tool demo. | 2014-09-08 | 08-Sep-2014: Action completed | 2014-09-08
10 | 2014-08-11 | Closed | All | Members of Mapping SIG to forward via email suggestions for agenda items. | 2014-09-08 | 08-Sep-2014: Suggestions received from one member. Discussed and agreed at the meeting. Close action | 2014-09-08
11 | 2014-09-08 | Open | IG | Organise a demonstration of the new SNOMED CT Browser during the face to face meeting sessions. | 2014-10-11
12 | 2014-09-08 | Open | IG | Arrange for an update on the joint work between IHTSDO and LOINC. | 2014-10-11
13 | 2014-09-08 | Closed | JRC/HB | Post draft agenda for face to face meeting. | 2014-09-09 | 09-Sep-2014: Action completed | 2014-09-09
14 | 2014-09-08 | Open | JRC/HB | Finalise agenda and post 2 weeks prior to meeting | 2014-10-13