| SNOMED CT Content Improvement Project Combined Inception and Elaboration phases |  |  |
| --- | --- | --- |
| Project ID: <id> Topic: Vital Signs Observable Entities |  |  |
| Date | 2014-11-17 |  |
| Version |  | 0.01 |

Amendment History

| Version | Date | Editor | Comments |
| --- | --- | --- | --- |
| 0.01 | YYYYMMDD | Daniel Karlsson | First draft for comments |
|  |  |  | (remove or add rows if necessary) |

Review Timetable

| Review date | Responsible owner | Comments |
| --- | --- | --- |
| YYYYMMDD | Person/group responsible | Summary of action |
|  |  | (remove or add rows if necessary) |

© International Health Terminology Standards Development Organisation 2012. All rights reserved.

SNOMED CT® was originally created by the College of American Pathologists.

The International Release of SNOMED CT® is distributed by the International Health Terminology Standards Development Organisation (IHTSDO), and is subject to the IHTSDO’s SNOMED CT® Affiliate Licence. Details of the SNOMED CT® Affiliate Licence may be found at http://www.ihtsdo.org/our-standards/licensing/.

No part of this document may be reproduced or transmitted in any form or by any means, or stored in any kind of retrieval system, except by an Affiliate of the IHTSDO in accordance with the SNOMED CT® Affiliate Licence. Any modification of this document (including without limitation the removal or modification of this notice) is prohibited without the express written permission of the IHTSDO.

Any copy of this document that is not obtained directly from the IHTSDO [or a Member of the IHTSDO] is not controlled by the IHTSDO, and may have been modified and may be out of date.  Any recipient of this document who has received it by other means is encouraged to obtain a copy directly from the IHTSDO [or a Member of the IHTSDO. Details of the Members of the IHTSDO may be found at http://www.ihtsdo.org/members/].

Table of Contents

1 Glossary	5

1.1 Domain Terms	5

2 Introduction	6

2.1 Purpose	6

2.2 Audience and stakeholder domain	6

2.2.1 Input from stakeholders	6

2.2.2 Degree of consensus on the statement of problem	6

3 Statement of the problem or need	7

3.1 Summary of problem or need, as reported	7

3.2 Summary of requested solution	7

3.3 Statement of problem as understood	7

3.4 Detailed analysis of reported problem, including background	7

3.5 Subsidiary and interrelated problems	7

4 Risks / Benefits	8

4.1.1 Risks of not addressing the problem	8

4.1.2 Risks of addressing the problem	8

5 Requirements: criteria for success and completion	9

5.1 Criteria for success/completion	9

5.2 Strategic and/or specific operational use cases	9

5.2.1 Use case 1	9

5.2.2 Use case 2…	9

6 Solution Development	10

6.1 Initial Design	10

6.1.1 Outline of initial design	10

6.1.2 Significant design or implementation decisions / compromises	10

6.1.3 Evaluation of Design	10

6.2 Iteration One	10

6.2.1 Outline of revised design	10

6.2.2 Significant design or implementation changes	10

6.2.3 Evaluation of Revised Design	10

6.3 Iteration Two ..	11

7 Recommendation	12

7.1.1 Detailed design final specification	12

7.1.2 Iteration plan	12

8 Quality program criteria	13

8.1 Quality metrics	13

8.1.1 Quality metric 1	13

8.1.2 Quality metric 2	13

8.2 Use case scenarios	13

8.2.1 Scenario One	14

8.2.2 Scenario Two	14

8.2.3 Scenario …	14

8.3 Test cases	14

9 Project Resource Estimates	15

9.1 Scope of construction phase	15

9.2 Projection of remaining overall project resource requirements	15

9.2.1 Expected project resource requirement category	15

9.2.2 Expected project impact and benefit	15

9.2.3 Indicative resource estimates for construction, transition and maintenance:	15

# Glossary

## Domain Terms

| vital signs | Merriam-Webster: signs of life; specifically : the pulse rate, respiratory rate, body temperature, and often blood pressure of a person |
| --- | --- |
| heart rate | Merriam-Webster: a measure of cardiac activity usually expressed as number of beats per minute |
| pulse rate | Merriam-Webster: the rate of the arterial pulse usually observed at the wrist and stated in beats per minute |
| blood pressure | Merriam-Webster: pressure exerted by the blood upon the walls of the blood vessels and especially arteries, usually measured on the radial artery by means of a sphygmomanometer, and expressed in millimeters of mercury either as a fraction having as numerator the maximum pressure that follows systole of the left ventricle of the heart and as denominator the minimum pressure that accompanies cardiac diastole or as a whole number representing the first value only |
| blood pressure | Kumar & Smith: Blood pressure is the pressure exerted on the arterial walls by the flow of blood. The term ‘blood pressure’ designates both a certain function (to exert pressure) and also a certain state (of pressure being exerted), both of which are dependent continuants, the latter being associated with a value. |
| blood pressure | Wikipedia: Blood pressure (BP), sometimes referred to as arterial blood pressure, is the pressure exerted by circulating blood upon the walls of blood vessels, and is one of the principal vital signs. When used without further specification, "blood pressure" usually refers to the arterial pressure of the systemic circulation, usually measured at a person's upper arm. A person’s blood pressure is usually expressed in terms of the systolic pressure over diastolic pressure and is measured in millimeters of mercury (mm Hg). |
| core temperature | Wikipedia: Core temperature, also called core body temperature, is the operating temperature of an organism, specifically in deep structures of the body such as the liver, in comparison to temperatures of peripheral tissues. Core temperature is normally maintained within a narrow range so that essential enzymatic reactions can occur. |
| core temperature | Merriam-Webster: the temperature deep within a living body (as in the viscera) |
| basal body temperature | Wikipedia: Basal body temperature is the lowest body temperature attained by during rest (usually during sleep). |
| basal body temperature | Merriam-Webster: the temperature of the body at rest that is typically taken immediately after waking from sleep |

# Introduction

## Purpose

The purpose of this project is to consider a templates for the representation of vital signs as SNOMED CT Observable entities using the draft Observable entity and Investigation procedure model.

## Audience and stakeholder domain

The audience for this document includes all standards terminology leaders, implementers and users. Investigations including vital signs, i.e. heart rate, respiratory rate, core body temperature and (systemic arterial systolic and diastolic) blood pressure, are frequently used in diagnostics and follow-up of treatment

A further significant audience is the community of SNOMED authors that may be requested to implement the recommended specification.

The IHTSDO Observable and Investigation Model Project is a stakeholder, and specifically the LOINC mapping subproject as the approx. 500 LOINC vital signs terms is to be mapped to the Observables model eventually.

### Input from stakeholders

The project has been worked on within the Observables project group and, specifically, a parallel modeling effort was performed with four modelers representing a (random) subset of existing vital signs observables.

### Degree of consensus on the statement of problem

-

# Statement of the problem or need

## Summary of problem or need, as reported

This document does not directly correspond to a IHTSDO content tracker artifact, other than the general artf6283 : Observables and investigation procedures redesign tracker item.

Vital signs is in scope of the LOINC mapping project.

## Summary of requested solution

No requested solution.

## Statement of problem as understood

To develop guidance for representation of SNOMED CT vital signs concepts (subsumed by 46680005 | vital sign (observable entity) |). While there are other concepts in other SNOMED CT hierarchies related to the vital signs observables, such as procedures and findings, these are considered out of scope of this project (see Table 1).

Table 1 Examples of related SNOMED CT concepts

| SNOMED CT hierarchy | Exampes |
| --- | --- |
| Clinical finding | 87273009 ¦ temperature normal (finding) ¦ 392570002 ¦ blood pressure finding (finding) ¦ |
| Procedure | 46973005 ¦ blood pressure taking (procedure) ¦ 408867002 ¦ taking respiratory rate (procedure) ¦ 72027000 ¦ radial pulse taking (procedure) ¦ |
| Physical object | 70665002 ¦ blood pressure cuff, device (physical object) ¦ 448349000 ¦ tympanic thermometer (physical object) ¦ |
| Situation with explicit context | 371622005 ¦ elevated blood pressure reading without diagnosis of hypertension (situation) ¦ 164286000 ¦ on examination - temperature not taken (situation) ¦ |

## Detailed analysis of reported problem, including background

### The generic observable entities model

There is currently no editorial guidance in the SNOMED CT concept model for representing Observable entities applied for the international release. Concepts in the Observable entity hierarchy are thus currently manually maintained. Small amounts of observables has been added over the years from 2002 to 2014 and as of 2015-01-31 the number of active concepts is 8373 (8281, 8274???) including the hierarchy root.

In 2006 an analysis of the contents of the Observable entity hierarchy was produced by David Markwell [Markwell2006]. In the analysis a number of issues are identified and described, focusing on Observable entities is proposed in the analysis, nor the development of such a concept model.

In 2008 an IHTSDO project was started with the aim of developing a concept model for the Observables entity hierarcy. The first meeting was held in Birmingham, UK 2008-07-01.

In 2009 a joint project with IHTSDO, Regenstrief Institute and IFCC-IUPAC (S)C-NPU as participants was started with the aim of testing a division of labor between IHTSDO and the laboratory medicine terminology development partners. A secondary aim was to test a then newly developed proposal for an Observables concept model.

A Draft Standard for Trial Use (DSTU) version of an Observables concept model was published 2010-06-30. The proposed model is informed by recent formal ontology developments, mainly the BFO  [BFO]. The model is fairly generic and thus, the challenge of using the model lies in its reproducible application across and within use cases.

### Vital signs observables current status

There are 134 SNOMED CT concepts subsumed by 46680005 | vital sign (observable entity) | in the 2015-01-31 release. 46680005 | vital sign (observable entity) | directly subsumes the four concepts 78564009 | pulse rate (observable entity) |, 86290005 | respiratory rate (observable entity) |, 386725007 | body temperature (observable entity) |, and 75367002 | blood pressure (observable entity) |. All concepts are, as in the rest of the Observable entity hierarchy, primitive.

It should be noted that 46680005 | vital sign (observable entity) | is a grouper of the four specific observables based on convention and cannot reasonably be fully defined. It should be considered whether or not a primitive grouper is the best way of representing such clinical conventions. Currently, due to the grouping, all current temperatures of the body, including e.g. 364511004 | ankle joint temperature (observable entity) |, are vital signs. Also, due to the primitive status of the grouper, body temperatures which do not explicitly or implicitly include an IS A relationship to 46680005 | vital sign (observable entity) | will not be subsumed by any modeled body temperature observables.

Although the four specific vital signs listed in SNOMED CT are generally agreed upon, there are also additional vital signs. E.g. the US PHIN, Public Health Information Network, lists 4 additional vital signs including head circumference, height, O2 saturation, and weight and the HITSP Consolidated CDA template for vital signs further lists an additional two: body surface area and BMI, thus including a total of 10 vital signs.

Each of the more specific kinds of observable will be described separately below.

### Process observables

The current draft Observables model contains a specific set of attributes for representing observables about processes (see Table 1). The ranges presented in the draft style guide v1.0 seems targeted towards laboratory medicine applications of the observables model, e.g. the restriction of process output to substances. Changes in range specifications to allow vital signs modeling using process observables is expected.

Table 2 Process observables attributes

| SNOMED CT attribute | Range |
| --- | --- |
| 704321009 ¦ characterizes (attribute) ¦ | <<415178003 ¦ process ¦ |
| 704322002 ¦ process agent (attribute) ¦ | <<123037004 ¦ body structure ¦ |
| 704323007 ¦ process duration (attribute) ¦ | <<7389001 ¦ time frame ¦ |
| 704324001 ¦ process output (attribute) ¦ | <<105590001 ¦ substance ¦ |

In earlier applications of the observables model, quality observables have been separated from process observables by distinct sets of allowed attributes. However, some of the vital signs observables are quality observables which are indirectly defined in terms of processes having the quality as a result. E.g. blood pressure is the result of the heart pumping blood (and other processes including kidney water reabsorption, vasoconstriction and –dilatation, etc. as well as other qualities, such as blood volume). Thus, for representing vital signs observables changes in how quality and process observables attributes are used is expected.

### Heart rate

In the 2015-01-31 release there are 8 heart rate observable concepts. Currently in SNOMED CT 78564009 | pulse rate (observable entity) | is the top concept among the heart rate observables and subsumes 364075005 | heart rate (observable entity) |. According to the definitions above “heart rate” would be the broader term.

### Respiratory rate

In the 2015-01-31 release there are 3 respiratory rate observable concepts. In addition to the generic respiratory rate concept, there are two respiratory rate observables related to ventilator treatment.

### Body temperature

In the 2015-01-31 release there are 36 body temperature observable concepts plus the concept 248458005 | comparative temperature in limbs (observable entity) | not subsumed by 386725007 | body temperature (observable entity) |. The concept 431807005 | temperature taken with digital thermometer (observable entity) | may or may not be interpreted as a kind of body temperature observable, although in the fully specified name it is not explicitly stated what the temperature inheres in.

There is a group of body temperature observables which aim to observe the core body temperature at different direct sites, e.g. the axilla (or the axillary pit), the mouth (or the sublingual space), tympanic membrane, etc. Among the body temperature concepts 9 are subsumed by 276885007 | core body temperature (observable entity) | while debatably 415922000 | forehead temperature (observable entity) | is often also an indirect measure of the core body temperature.

Two concepts 248430002 | pattern of fever (observable entity) | and 248431003 | phase of fever (observable entity) | are not considered body temperature observables and thus considered out of scope of this work.

### Blood pressure

In the 2015-01-31 release there are 87 blood pressure observable concepts plus an additional 30 concepts subsumed by 165077006 | intracardiac pressure (observable entity) | but not currently subsumed by 75367002 | blood pressure (observable entity) |. It should be considered whether blood pressure observables should include both pressures inside blood vessels and the heart or only the blood vessels. From a clinical perspective, the boundary may not always be clear. E.g. the central venous pressure, measured in the superior vena cava close to the right atrium, is often an estimate of right atrial pressure.

It is here assumed that blood is the fluid that flows in the spaces of the cardiovascular system or, alternatively, that “blood pressure” would be the pressure exerted by any fluid, e.g. a resuscitation fluids or blood substitute, on the walls of the spaces of the cardiovascular structures.

It has been discussed what blood pressures inhere in: the vessels and the heart, the endothelium, the inner surface of the hollow cardiovascular structures, the fluid, typically the blood, or the spaces or lumens of the cardiovascular structures, or any combination of those entities.

Blood pressure observables are typically specified in terms of points in time in relation to the cardiac cycle, or as an aggregate over the cardiac cycle: mainly systolic pressure (max arterial pressure over a cycle) and diastolic pressure (min arterial pressure over a cycle), but also a wave, v wave, x trough, and y trough. Further, blood pressures are often aggregated over several cardiac cycles, e.g. minimum/maximum/average 24 hour systolic blood pressure. Thus, there are two levels of process where one aggregate process may consist of specified parts of underlying cardiac cycles (see Figure 1).

Figure 1 Heart beating processes

Often the term “blood pressure” is used to only refer to systemic arterial pressure, and cases where this is clear, for example as used in data capture forms, such blood pressure concepts should not subsume other kinds of blood pressure.

## Subsidiary and interrelated problems

artf6283 : Observables and investigation procedures redesign

LOINC mapping project

# Risks / Benefits

## Project Risk Profile

The project risk profile is determined using the project risk profile assessment instrument as described in the “Guide to Stakeholder Engagement in Content Development” document.

| Criteria | Analysis | Score |
| --- | --- | --- |
| Number of concepts affected | Ca 130 | 1 |
| Number of users affected | Vital signs are commonly used. SNOMED CT users in LOINC-using jurisdictions would potentially use LOINC instead. | 2 |
| Changes to vendor software required | Use of OWL beyond what is possible in RF2 is foreseen. | 1 |
| Change to concept model | Use of existing draft Observables model, possibly with new attributes or new ways of applying attributes | 1 |
| Change to content development software or processes | No changes foreseen | 0 |
| Average score |  | 1 |

Controversy level is assumed to be medium-low, a score of 1, …

According to the project risk profile instrument the project is of low risk. The proposed project stakeholder engagement approach is indirect consultation of a larger number (> 10) of users/groups.

### Risks of not addressing the problem

The SNOMED CT Observables entity content is currently, due to the lack of any formally defined content, manually maintained. Issues with current content has been identified in the Observables hiereachy, e.g. by Markwell [Markwell2006], in the IHTSDO-WHO ICF harmonization work [WHOFIC-Showcase2013 poster], and not least by the IHTSDO Observable and Investigation Model project [CollabNet].

Information model development teams such as CIMI [e.g. the CIMI Observation archetype] and the VA LEGO project [reference?] have identified extensions compared to current Observables content. Scalable extension of Observables content is highly likely to require the possibility to fully define SNOMED CT concepts.

### Risks of addressing the problem

A potential result of applying a model to the vital signs content in SNOMED CT is that existing concepts could be re-classified. Users assuming the current structure of vital signs content will have to adopt to those changes.

Any concept model aiming to entirely cover Observable entity content will by necessity be generic in nature. Unconstrained use of a generic model may lead to inconsistent modeling, as there will often be alternative solutions to representing specific content use cases.

# Requirements: criteria for success and completion

## Criteria for success/completion

## Strategic and/or specific operational use cases

The project’s main fit with IHTSDO strategic use cases is for 1E Order communication and result reporting. Investigations of vital signs are frequently reported but is probably less frequently specifically ordered.

### Use case: 1E Order communication and result reporting

#### Fit with IHTSDO strategy

Quote from SNOMED CT Detailed Content Development Plan 2011-2015:

“3.3.4 Order entry and result reporting

Scope: revision of observables and observation procedures, for laboratory and clinical uses.

Included in scope: coordination with external vocabularies such as LOINC and cNPU. Also included in scope is the coordination of definitions of clinical observations of functioning and disability that relate to WHO classifications, particularly the International Classificaiton of Functioning and Disability (ICF).  Result reporting has broad scope, including radiology and other imaging, laboratory (clinical pathology), anatomic pathology, pulmonary function, electrocardiogram, and so forth.

Out of scope: a formal mapping from all of SNOMED CT to all of ICF is out of scope.

Project interactions:

Observables depend on anatomy, substances, organisms, and a revision of the current parts of the observables hierarchy that are under “process”, including activities and physiological actions.”

# Solution Development

## Initial Design

### Outline of initial design

The solution applies the existing draft observables model for currently existing SNOMED CT observables. However, experiments performed in the Observables project group show that with additional attributes and extended (or clarified) used of existing attributes, more Observables may be fully defined.

#### Process observables (Heart rate and Respiratory rate)

Process observables are observables which are about process qualities, qualities that inhere in processes according to BioTopLite. Both heart rate and respiratory rate are number rates, i.e. the number of entities, here cardiac and ventilation cycles, “produced” by the process per unit of time.

Figure 2 Definition of Heart rate (observable entity)

Here, the heartBeatingProcess is the continuous process of heart contraction and relaxation (see Figure 2). TODO: add nesting, i.e. Observation procedure – Feature

This definition of heart rate is similar to, at least one perspective of, other process observables having specific output, such as excretion observables. The difference here is that an excretion process has continuant material entities as output while these processes have certain types of process parts as output.

Figure 3 Heart rate classification results

A Heart rate observable is defined as any observable which observes this process quality and a Pulse rate observable is defined as any observable which observes this process quality at the direct site of a specific systemic artery (see Figure 3).

Figure 4 Definition of Respiratory rate (observable entity)

A Respiratory rate observable is defined likewise, with ventilationCycle replacing cardiacCycle (see Figure 4).

Figure 5 Respiratory rate classification result

The two observables Rate of spontaneous respiration and Total breath rate, both relating to ventilator treatment, are primitive.

#### Body temperature

Body temperature is defined as any temperature that inheres in any (anatomical or acquired) body structure (see Figure 6).

Figure 6 Definition of Body temperature (observable entity)

There are two kinds of body temperature observable: core body temperature observable and specific anatomy temperature observable. The core body temperature inheres in 278826002 | body internal region (body structure) | representing the non-superficial parts of the body. The ‘direct site’ attribute specifies the site of measurement (see Figure 7). However, 278826002 | body internal region (body structure) | is a leaf node in SNOMED CT and does not subsume any of the structures considered to be contained in the body internal region, such as e.g. the viscera. Thus, temperatures of specific internal body parts are not automatically classified as core body temperatures.

Figure 7 Definition of Core body temperature, measured at tympanic membrane (observable entity)

The specific anatomy temperature observables are more straight-forward. The temperature qualities inhere in the specific body structure, as e.g. in Figure 8.

Figure 8 Definition of Knee joint temperature (observable entity)

There are two primitive concepts among the body temperature observables: Basal body temperature and Peripheral body temperature. Basal body temperature is the minimum “normal” core body temperature during rest, i.e. not related e.g. to hypothermia or other non-normal conditions. Thus, basal body temperature cannot just be defined as an aggregate minimum temperature. Peripheral body temperature cannot be fully defined, unlike core body temperature, because there is no single SNOMED CT concept corresponding to ‘peripheral body region’.

Figure 9 Body temperature classification results

### Significant design or implementation decisions / compromises

### Evaluation of Design

#### Exceptions and Problems

#### Design Strengths

#### Design Weakness

#### Design Risks

| Description of risk | Importance | Mitigation plan |
| --- | --- | --- |

## Iteration One

### Outline of revised design

Redesign the Solution Identify objectives of iteration, and the major changes to previous design

Communicate the revised design

### Significant design or implementation changes

### Evaluation of Revised Design

#### Exceptions and Problems

#### Design Strengths

#### Design Weakness

#### Design Risks

| Description of risk | Importance | Mitigation plan |
| --- | --- | --- |

## Iteration Two ..

# Recommendation

### Detailed design final specification

Design the Solution Identify major design elements and how they collaborate to realize the scenario

Communicate the design

### Iteration plan

# Quality program criteria

## Quality metrics

### Quality metric 1

| Component | Characteristic and Description |  | Metric | Target | Result |
| --- | --- | --- | --- | --- | --- |
| Logic definitions of concepts in <domain> | Char: | sufficiently defined | - Proportion sufficiently defined - Numerator: count of those defined. - Denominator: count of all concepts under <concept nnnnn> | 95% |  |
|  | Descr: | Concept logic definitions should be “defined” not “primitive” |  |  |  |

### Quality metric 2

| Component | Characteristic and Description |  | Metric | Target | Result |
| --- | --- | --- | --- | --- | --- |
| Fully specified names in <domain> | Char: | Adherence to terming guidelines | - Proportion meeting guidelines, based on manual review | 100% |  |
|  | Descr: | The fully specified name should adhere to terming guidelines listed in the editorial guide, sections <list sections> |  |  |  |

## Use case scenarios

#### Create Test Cases: Review the requirements to be tested as set out in the Inception Phase document. Identify and outline relevant Test Cases. Identify test data needs. Share and evaluate the Test Cases

### Scenario One

#### Expected Setting

#### Data capture requirement

#### Data retrieval requirement

### Scenario Two

#### Expected Setting

#### Data capture requirement

#### Data retrieval requirement

### Scenario …

## Test cases

# Project Resource Estimates

Estimate project size; Forecast project velocity and duration

Evaluate risks; Establish costs and articulate value; Plan deployment; Outline project lifecycle

## Scope of construction phase

Optionally:

Skills required

Solution Specification (Elaboration)

Implementation

Outline of work packages

Preventing recurrence of problem

Division of project into stages

## Projection of remaining overall project resource requirements

### Expected project resource requirement category

Is it “fast track” or does it require project management?

### Expected project impact and benefit

Updated view of impact and benefit, organized by stage if the project is to be staged

### Indicative resource estimates for construction, transition and maintenance:

Construction and transition phase: 	100-200 new concepts to be authored

Maintenance phase:	500-1000 new ‘frequent usage’ concept requests in 1st 3 years

Kumar, A., & Smith, B. (2004). The ontology of blood pressure: a case study in creating ontological partitions in biomedicine. http://ontology.buffalo.edu/medo/BPO.pdf

http://www.ifomis.org/bfo/home

https://phinvads.cdc.gov/vads/ViewValueSet.action?oid=2.16.840.1.113883.3.88.12.80.62

http://purl.org/biotop

An alternative perspective on excretion processes is that they do not have any output but transports entities from one place to another.