## Slide 1: Microbiology Project Group
John Snyder, DTR, RD – Co-chair

## Slide 2: Scope Statement
Identify concepts from the organism hierarchy (i.e. < 410607006 |Organism (organism)|) that exist in the extension modules of participating NRCs that are eligible for promotion, with appropriate reference to authoritative source material, to the international edition and define a process for having content promoted on an ongoing basis
Notes: -
Define what should be in the organism hierarchy versus what should be in the finding hierarchy?

## Slide 3: MALDI-TOF
Member request
  Align SNOMED Organism hierarchy with MALDI-TOF’s mass spectrometry database of organism
Review
  No one single authoritative MALDI-TOF mass spectrometry database
  Each country / organization selects which organism that will be represented in their MALDI-TOF implementation
  Curator’s of MALDI-TOF content rely on same authoritative sources as SNOMED International (e.g. LPSN, Mycobank, etc.)
Proposal
  MALDI-TOF is out-of-scope for the microbiology project group
  Member request SNOMED International pursue formal partnership with organism authoritative source curator’s and establish:
    Agreement for full representation of authoritative source content in SNOMED Organism Hierarchy
    Process for consuming and updating content from authoritative sources

## Slide 4: Project Task List
Project Team NRCs
  Extract extension level content from < 410607006 |Organism (organism)| into SNOMED CRS batch template (Excel)
    IF an NRC has ability to query SNOMED using transitive closure against the FULL RF2 files should provide earliest effectivetime for all concepts eligible for promotion
  Identify supporting references from recognized authoritative Source(s)
  Each NRC will be responsible for review of internal content for concepts that are based on homonyms and/or basonyms for inactivation
Project Administrator
  Cross-walk submitted content from member NRCs to identify overlapping content
    NRC to provide earliest effectivetime for overlapping organisms
  Concept with earliest effectivetime becomes the “ideal candidate for promotion”
Content Promotion
  Phase 1: overlapping content promoted to core edition
  Phase 2: non-overlapping content with references from authoritative sources to be promoted

## Slide 5: Project Business Rules
Non-overlapping content
  Defined as any organism concept that exists in a single national extension and meets the criteria for promotion to the International edition
  does not need to be evaluated by the project group prior to submission to international for promotion
  Promotion request for all content in < 410607006 |Organism (organism)| that is eligible for promotion should be made as soon as possible.
Overlapping Content
  Defined as any organism concept that exists in two or more national extensions and meets the criteria for promotion to the international edition
  Project group will review and evaluate each concept for promotability
  Concept with the earliest concept creation effectivetime is considered the “Ideal promotable concept”
    So that all NRCs are fairly represented in this decision, criteria other than effectivetime will not give weight to the decision. (e.g. Size or age of an NRC)
  The NRC that owns the “Ideal promotable concept” may decline to have their content promoted. In which case, the next concept in line based on effectivetime will become the “ideal promotable concept”

## Slide 6: Batch Template Column Repurposing
Batch template should be populated as expected with the following exceptions
  Parent Concept Id(1) and Parent Concept Id(2)
    Based on transitive closure with depth, this is the most immediate parent concept(s)
  Parent Concept Id(3)
    Grouping concept that contains the conceptID only for one of the following concepts so that we can filter the content from each extension by domain for working purposes
      419036000 |Domain Archaea (organism)|
      409822003 |Domain Bacteria (organism)|
      415671008 |Domain Eukarya (organism)|
      84676004 |Prion (organism)|
      49872002 |Virus (organism)|
  Proposed Use
    contains static text “Organism project group - Promotion of extension content”
  Summary
    Repurposed to contain the effectivetime the concept was created in a particular extension from the FULL RF2 concept file

## Slide 7: US NRC Analysis and example
Content eligible for promotion
  419036000 |Domain Archaea (organism)| - 0
  409822003 |Domain Bacteria (organism)| - 59 (57)
    Urgent promotion request submitted by Estonia for
      471251000124108 |Microbacterium radiodurans (organism)|
      541371000124102 |Flavimobilis soli (organism)|
  415671008 |Domain Eukarya (organism)| - 571
  84676004 |Prion (organism)| - 0
  49872002 |Virus (organism)| - 8
Review of batch submission