## Slide 1: Cancer Synoptic Reporting Working Group Update
W. Scott Campbell, PhD, MBA
Peter Hinrichs Professor and Chair of Pathology Informatics
University of Nebraska Medical Center

## Slide 2: Concepts made/edited to date
SNOMED CT Hierarchy | New or edited concepts developed (1) | New or edited concepts mapped to CAP cancer protocols (2) | Mapped SNOMED CT concepts to CAP cancer protocols (3)
Observable entity | 1010 | 585 | 664
Morphologic abnormality | 76 | 54 | 430
Qualifier value | 73 | 37 | 175
Disorder | 53 | 0 | 38
Substance | 42 | 0 | 1
Staging scale | 12 | 0 | 0
Situation | 3 | 0 | 1
Procedure | 1 | 1 | 166
Specimen | 1 | 0 | 10
Total | 1326 | 698 | 2013
Table 1 – SNOMED CT concepts by SNOMED CT top level hierarchy. Column 1 represents new and/or edits SNOMED CT concepts developed in this project by top level hierarchy. Column 2 indicates the number of new and/or edited concepts mapped to CAP cancer protocol data elements. Column 3 represents the total number of mapped SNOMED CT concepts to CAP cancer protocol data elements.

## Slide 3: Protocol Binding Status
College of American Pathologists (CAP)
37/51 Adult data sets validated by CAP.
Remaining 14 adult binding validations to be done by 12/31/24.
Pediatric data sets to be validated early 2025
CAP to distribute bindings with their electronic Cancer Protocol (eCP) distribution to EHR and LIS vendors
International Collaboration on Cancer Reporting (ICCR)
ICCR binding validation at beginning stages
Largely a repeat of the CAP process with exception of unique data elements
Meetings to resume in November.

## Slide 4: Ongoing Work
Limited terminology development work
  ICCR unique terms
  Anatomic locations not currently present in SNOMED CT (ex. Lymph node locations)|
Resolution of existing “finding” content
Binding of ICCR data sets and inclusion in Implementation Guide

## Slide 5: End Date and New Work
CSRWG Status
CSRWG to formally end as a working group by Spring Business Meeting (2025)
Work goes to maintenance
Governance/process to be worked out
(Working groups ideally have a start and end.)
Histology Quality Working Group
Align SNOMED CT histology content with Blue Book version 5 and ICD-O-4
Ensure histology lineages and groupings are conformant to current biologic understanding
Chair – Scott Campbell. Co-chairs – Brian Rous and Thomas Rudiger
Potential groups:
Immunohistochemistry
Whole slide imaging
Medical Kidney
Others?

## Slide 6: Questions