## Slide 1
OCTOBER 2024 SNOMED INTERNATIONAL BUSINESS MEETINGS
MONDAY OCTOBER 21, 2024 SEOUL, REPUBLIC OF KOREA
Leading healthcare terminology,
worldwide
French translation of
SNOMED CT Foundation Course
Part II – Evaluation & Conclusion
NRC Belgium

## Slide 2
Agenda
    Translation project – resume
    Results
    Evaluation - Lessons learned
    Conclusion & Next steps

## Slide 3
Photo by Humphrey Muleba: https://www.pexels.com/photo/photo-of-black-vehicle-at-the-road-1647120/
Purpose – objectives
  Providing a French version of (a part of) the new/revised SNOMED CT Foundation Course - reference document for eLearning participants
  Support local stakeholders with localized materials to overcome language barriers for acquiring knowledge and expertise related to SNOMED CT
  Test translation of SNOMED CT materials by students without clinical background (PoC)
Scope
  Slide decks in PowerPoint
  Subtitles in .srt format (plain text file that contains the timing when subtitle is shown in the video)
  Exercises + assessments (Moodle quiz activity) => out of scope
Translation project - resume

## Slide 4
Photo by Humphrey Muleba: https://www.pexels.com/photo/photo-of-black-vehicle-at-the-road-1647120/
Phases
Translation project - resume
2023
Translations (c’ted)
Evaluation/correction results
Preparing next phase
2024
Clinical validation
Evaluation/corrections
Consolidation
2022
Start project with UMons
Briefing/training of students
Start translations

## Slide 5
Outcome
Translation – phase 1 (students linguistics)
  Quality of translations quite temperamental because many students participated, each contributing to small parts of the course
  Sometimes insufficient terminological precision
    Produced by translation students without clinical expertise
  Sometimes inconsistencies and inappropriate terminology
    Lack of SNOMED CT knowledge
  QA checks improved the linguistic quality of the initial version
Clinical validation – phase 2 (medical experts)
  Clinical domain experts reviewed the translations to ensure that the terminology was accurate and appropriate for healthcare professionals (alignment with target audience)
  Sometimes inconsistencies
    Lack of SNOMED CT knowledge
Results

## Slide 6
Evaluation
Is it possible to have SNOMED material translated by non-clinical profiles ?
  Yes, it is possible to have SNOMED material translated by non-clinical profiles, in particular by professional translators
  Possible but sufficient? Collaboration with clinical experts is essential, as the translated terminology needs to be validated by domain experts to avoid that incorrect translations would lead to errors in the interpretation of clinical concepts
  Quality depends on
    Individual proficiency in English and French
    Knowledge of SNOMED CT
    Experience with clinical practice
    Familiarity with eLearning materials
Lessons learned

## Slide 7
Evaluation
Has clinical validation helped or complicated matters?
  Validation has greatly helped to improve the quality of translation but it has also made the process more complex
  Volumes are too big to ask a clinical expert to translate from scratch. Still also the validation itself took a considerable amount of time, slowing down the process
  Involving clinical experts is necessary to ensure accurate terminology of clinical concepts, even though working with multiple resources for validation may introduce inconsistencies at different levels
  Quality depends on
    Individual proficiency in English and French
    Knowledge of SNOMED CT (on top of medical domain knowledge)
Lessons learned

## Slide 8
Lessons learned
What were strong points?
  Interdisciplinary collaboration between translators and clinical experts to ensure accurate translation of terms
  Improvement in terminological precision through clinical validation
  Central coordination for consitency and QA
What were main challenges?
  Complexity of medical terminology
  Multiple iterations to ensure consistency
  Finding equivalents in French for specific medical concepts
  Increased timeline due to successive phases of clinical validation and necessary adjustments
What are good practices?
  Involve clinical experts early in the translation process to avoid inconsistencies (multidisciplinary team)
  Utilize pilot testing by allowing a small group of end users to use the translated material, identifying potential issues early before wider deployment (Common French ?)

## Slide 9
  Valorisation & maintenance of the materials
  To optimise its use, the translated version should be regularly updated in line with developments in the original version
  As Is: reference/support document with slides and transcripts
  To Be: hosting of subtitles?
  Commitment of French Translation Group NRCs
  Ownership of French version SNOMED CT Foundation
  SPOC for questions of students
  Translation of remaining parts (exercises + assessments)
  Proposal to meet with SI/ELAG for further steps
Conclusion & next steps

## Slide 10
OCTOBER 2024 SNOMED INTERNATIONAL BUSINESS MEETINGS
Leading healthcare terminology,
worldwide
THANK YOU