## Slide 1: LOINC – SNOMED CT Cooperation on Content
Overview for IHTSDO Business Meetings
April 2016
London, England

## Slide 2: Background
Cooperative agreement between RII and IHTSDO, July 2013
  Builds on strengths of each terminology
  Minimize and manage duplication
  SNOMED CT and LOINC work better together
  Provide links between LOINC and SNOMED CT

## Slide 3: Value
Greater consistency in coding of order entry and results reporting
Improvements in each terminology
Improved analytics and quality control
  Query LOINC via SNOMED CT hierarchy and relationships
  Better identification and maintenance of laboratory tests value sets for public health reporting
  Enhanced tracking and management of infectious disease outbreaks
Integrates disparate elements in EHRs
  Lab test in LOINC with elements in patient chart in SNOMED CT (e.g. allergies, chief complaint, vital signs, age)
  Enables clinical decision support, may aid in reimbursement

## Slide 4: Roles of individuals and groups
Internal project team – currently 7 individuals
  Business Services Executive, Head of Education, Release Manager, Digital Product Architect, Head of Terminology, Terminologists
LOINC project team contacts
Executive Policy Group (3 from RII and 3 from IHTSDO)
Observable and Investigation Model Project
  Subproject on CollabNet (those interested in participating contact SSA or FAS)
Project groups and Special Interest Groups (e.g. Substance Redesign, IPaLM SIG , Organism and Infectious Redesign)
External collaborators:
  Kaiser Permanente
  US Veterans Administration
Notes: IHTSDO individuals and roles: Business Services Executive – Ian Green
Head of Education – David Markwell
Release Manager – Andrew Atkinson
Digital Product Architect – Robert Turnball
Head of Terminology – James Case
Terminologists – Farzaneh Ashrafi and Suzanne Santamaria

## Slide 5: Project scope
Scope
  Laboratory LOINC
  Vital signs
  Physiologic measurements
  Anthropomorphic measurements and evaluations
Phases
  Initial
    Top 2000 lab LOINC tests
    Microbiology
    Chemistry
    Vital signs
  Subsequent
    Remainder of lab LOINC
    Measurements

## Slide 6: Development phase objectives
Collaboration
  Invite participation by stakeholders
  Regular meetings (internal group; EPG; KP)
  Ensure approach works with concurrent projects (e.g. Substance Redesign, Vital signs)
  Publicize work and progress
Content development
  Add and update content to SNOMED CT to complete the LOINC Parts map (techniques, substances, etc.)
  Determine the best approach for handling complex concepts
  Create documentation of process and outcomes
  Create and deliver alpha release and Technology Previews
Test and obtain feedback
  Document and test the Observables model (including description logic)
  Document the quality test plan
  Review feedback on releases from stakeholders

## Slide 7
Map LOINC parts
to SNOMED
Jan 2014
April 2014
Map LOINC codes
to SNOMED
expressions
Roadmap
Alpha release – Phase 1-3
Candidate baseline Release (Beta)
Alpha prototype (owl)
August 2016
October 2014
Develop
distribution
format
LOINC Answer sets mapped to SNOMED codes
Business Meeting
Business Meeting
Business Meeting
September 2015
Business Meeting
April 2016

## Slide 8: Progress
Collaboration
  Regenstrief Institute
  IPaLM SIG, Project groups (Substance, Organism Redesign, and Observable Redesign projects) engaged
  Regular meetings held (internal group; EPG; KP)
  Posters at 2014 ICBO and SNOMED CT Showcase
  Presentation at 2015 SNOMED CT Showcase
Content development
  SNOMED CT concepts added for LOINC Part mapping, metadata, etc.
  Draft implementation guidance released July 2014
  alpha release released May 2014 with documentation
    117 LOINC Terms
  Development of Technology Preview Structure Process
  Technology Preview released October 2014 with documentation
    2100 LOINC Parts in LOINC Part to SNOMED RefSet
    9700 LOINC Terms in LOINC Term to Expression RefSet

## Slide 9: Progress continued
  Evaluation of the feedback received on the first version of the technology preview regarding release format and content
  Second Technology Preview released in September 2015 with documentation
    4061 LOINC Parts in LOINC Part to SNOMED CT RefSet
    14736 LOINC Terms in LOINC Term to Expression RefSet
  Alpha – Phase 3 released on April 1, 2016 with documentation
    Main objective: Change format of expressions from nested to flat
    Included minor changes in content, based on the feedback on the previous releases
      4051 LOINC Parts in LOINC Part to SNOMED CT RefSet
      13620 LOINC Terms in LOINC Term to Expression RefSet
    Due date to provide feedback: May 31, 2016

## Slide 10: Progress Continued
Test and obtain feedback
  Report on implementation horizon and scope released April 2014
  Performed quality test plan for functionality and reproducibility
  Analyzed feedback on alpha prototype, first and second release of Technology Preview and modified content accordingly
  Documented and tested the Observables model, in nested and flattened format (including description logic and creation of OWL ontology).

## Slide 11: Next steps
  Evaluation of feedback on Alpha release, Phase 3 – Spring 2016
  Prepare and release Candidate Baseline– Summer 2016
  Finalize map of LOINC Parts to SNOMED CT concepts – Pending receiving full set from RII
  Resolve some known/upcoming complex content issues
  Implement SNOMED CT Observables model to define existing pre-coordinated SNOMED CT concepts – Pending implementation of Observable model and development of tooling

## Slide 12: Contact information
Feedback on Alpha release – phase 3 (using JIRA Tracking Tool in Confluence)
  https://confluence.ihtsdotools.org/display/OBSERVABLE/LOINC+Alpha+Release+Feedback
General queries to IHTSDO Project Team
  info@ihtsdo.org
  Subject: LOINC – SNOMED CT Cooperation Project

## Slide 13: References
Content
  Alpha release files of LOINC - SNOMED CT Cooperation Project, including additional file formats (OWL, Excel) are available at: https://mlds.ihtsdotools.org/#/ihtsdoReleases/ihtsdoRelease/50041
Implementation
  Guidelines for using SNOMED CT and LOINC together - Phase 2 Draft: http://snomed.org/snomedloinc
Observables redesign
  https://confluence.ihtsdotools.org/display/OBSERVABLE/Observable+and+Investigation+Model+Project+Home
RII – IHTSDO Agreement
  http://www.ihtsdo.org/about-ihtsdo/partnerships/loinc

## Slide 14
QUESTIONS & DISCUSSION