| A Guide to Stakeholder Engagement in Content Development |  |  |
| --- | --- | --- |
| This document describes the criteria and processes to be used when engaging stakeholders for sustainable quality content development |  |  |
| Date | 20130303 |  |
| Version |  | 1.0 |

Contributing Authors (Class of 2012/13):

Jane Howarth

Cathy Richardson

Geraldine Wade

Paul Amos

Robert Hausam

Kin Wah Fung

Herman Muys

Shapoor Shayegani

Amendment History

| Version | Date | Editor | Comments |
| --- | --- | --- | --- |
| 0.01 | 20121218 | G Wade | Initial draft for comments |
| 0.02 | 20130124-30 | J Howarth | Integration of additional content; second draft for comments |
| 0.03 | 20120130-07 | J Howarth | Incorporate revised content and comments received; third draft |
| 0.04 | 20130218 | H Muys | Reworked section “3 Identification of Roles and Responsibilities in the Stakeholder Engagement Process” |
| 0.09 | 20130220 | P Amos | Editorial amendments to bring consistency of style and addressing content gaps |
| 1.0 | 20130303 | P Amos | Revised following feedback from K Spackman & Group |

Review Timetable

| Review date | Responsible owner | Comments |
| --- | --- | --- |
| YYYYMMDD | Chief Terminologist | Summary of action |
|  | Content Committee | (remove or add rows if necessary) |
|  | Content Development Manager |  |
|  | Quality Committee |  |

© International Health Terminology Standards Development Organisation 2013. All rights reserved.

SNOMED CT® was originally created by the College of American Pathologists.

This document forms part of the International Release of SNOMED CT® distributed by the International Health Terminology Standards Development Organisation (IHTSDO), and is subject to the IHTSDO’s SNOMED CT® Affiliate Licence. Details of the SNOMED CT® Affiliate Licence may be found at http://www.ihtsdo.org/our-standards/licensing/.

No part of this document may be reproduced or transmitted in any form or by any means, or stored in any kind of retrieval system, except by an Affiliate of the IHTSDO in accordance with the SNOMED CT® Affiliate Licence. Any modification of this document (including without limitation the removal or modification of this notice) is prohibited without the express written permission of the IHTSDO.

Any copy of this document that is not obtained directly from the IHTSDO [or a Member of the IHTSDO] is not controlled by the IHTSDO, and may have been modified and may be out of date.  Any recipient of this document who has received it by other means is encouraged to obtain a copy directly from the IHTSDO [or a Member of the IHTSDO. Details of the Members of the IHTSDO may be found at http://www.ihtsdo.org/members/].

Table of Contents

Glossary	4

Domain Terms	4

1 Introduction	5

1.1 Purpose and Scope	5

1.2 Out of Scope	6

2 Principles and Criteria for Undertaking Stakeholder Engagement	7

2.1 Benefits	7

2.2 Criteria for Successful Engagement	7

2.3 Stakeholder Involvement in the Content Development Process	7

3 Stakeholder Engagement Process	9

3.1 Introduction	9

3.2 Content Development Project Initiation	9

3.3 Define Purpose, Scope and Desired Outcome of Stakeholder Engagement	11

3.4 Assess the Project Risk Profile	11

3.5 Select Method of Stakeholder Engagement	13

3.6 Identification of Stakeholders	16

3.6.1 Engagement Activities of Stakeholders	16

3.6.2 Stakeholder Identification and Analysis	17

3.6.3 Roles and Responsibilities	19

4 Optimizing Stakeholder Engagement	21

4.1 Criteria for Successful Stakeholder Engagement	21

4.1.1 Criteria to Define Successful Stakeholder Engagement	21

4.1.2 Criteria to Measure Successful Stakeholder Engagement	22

4.1.1 Criteria to Determine When Stakeholder Engagement Has Been Successfully Completed	22

4.1.2 Potential Additional Quality Indicators for Adequate Stakeholder Engagement	23

4.2 Potential initial activities to support stakeholder engagement	24

5 Summary	25

Appendix A: References	26

# Glossary

## Domain Terms

| Stakeholder engagement | The process used by an organization to engage relevant stakeholders for a clear purpose to achieve accepted outcomes. Stakeholder engagement drives strategic direction as well as operational excellence. |
| --- | --- |
| Stakeholders | Those individuals, groups of individuals or organizations that affect and/or could be affected by the organization’s activities, products or services and associated performance with regard to the issues to be addressed by the engagement. |
| Quality | Fit for purpose. Related to consistency as well as usability, reproducibility and usefulness |

# Introduction

Many leading companies and organizations have begun to develop an appreciation that stakeholder engagement can positively contribute to product and service innovation, corporate quality and governance processes.  More importantly there is a growing realization that stakeholder engagement can lead to the achievement of sustainable benefits to both the company and it’s clients that could not have been realized by the organization’s efforts alone.

Development of sustainable quality terminology content requires the pooling of diverse perspectives, knowledge and resources. No individual, professional association or Standards Development Organization (SDO) is likely to have sufficient resources or the specialist knowledge base required to develop and maintain a clinical terminology such that it meets the needs of the international community of practice and supports a comprehensive, accurate and interoperable electronic health care record.

In addition, there is an increasing awareness that even small changes to SNOMED CT content and structure can have significant direct or indirect impact on implementers and users; therefore it is essential that the community of practice has the opportunity to assess the impact and influence the development process.

Given this, the objective of stakeholder engagement as it relates to the ongoing development, maintenance and uptake of SNOMED CT® is to support the delivery of effective, sustainable, quality content development by involving relevant stakeholders at appropriate points throughout the IHTSDO Content Development Process.

## Purpose and Scope

The purpose of this document is to provide a framework for stakeholder engagement that may be applied to either the Fast Track or standard content development process that comprises the following stages:

- Inception

- Elaboration

- Construction

- Transition

With regard to ‘content development’ the following is considered to be within scope:

- Concepts

- Descriptions

- Relationships

- Concept model

- Reference Sets

- Editorial guidelines

This document is designed primarily for use by SNOMED CT content developers, terminology editors, Consultant Terminologists and other stakeholders directly engaged in, or, monitoring the IHTSDO Content Development Process from which the international release of SNOMED CT is derived.

This approach is intended to support the editing and authoring community such that terminology content development is aligned with the requirements of the user base and with the strategic and quality objectives of the IHTSDO.

## Out of Scope

The following are considered to be out of scope:

- File structure

- Release formats and processes

- Mapping

- Translations

- National/Local extensions to SNOMED CT

- Workbench

However, the approach and methodology outlined within this document could be adapted for use in any of the above and in particular it is suggested that Local Release Centers consider this approach in support of their own content development process.

# Principles and Criteria for Undertaking Stakeholder Engagement

The Glossary defines Stakeholder Engagement as “the process used by an organization to engage relevant stakeholders for a clear purpose to achieve accepted outcomes. Stakeholder engagement drives strategic direction as well as operational excellence”.

## Benefits

The potential benefits of effective and strategically aligned stakeholder engagement are defined within the A1000 Stakeholder Engagement Standard 2011 and are listed below. In summary, they can:

- Lead to more equitable and sustainable development by giving those who have a right to be heard the opportunity to be considered in the decision-making processes

- Enable better management of risk and reputation

- Allow for the pooling of resources (knowledge, people, money and technology) to solve problems and reach objectives that cannot be reached by single entities or organizations alone

- Enable understanding of a complex business environment, including market developments and identification of new strategic opportunities

- Enable organizations to learn from stakeholders, resulting in product and process improvements

- Inform, educate and influence stakeholders and the business environment to improve their decision-making and actions that impact on the organization, and, most importantly;

- Build trust between the organization and its stakeholders

## Criteria for Successful Engagement

Stakeholders will judge the effectiveness of the organization’s stakeholder engagement strategy and processes against 3 main ‘principles’:

- Genuine - Is it genuine? Is the organization just going through the motions of consultation for public relations purposes, or, is the organization serious about getting a complete and balanced picture of the material impacts of its work

- Fair and well-informed – Is it fair and well informed? Does the engagement process allow all (relevant) stakeholders to be considered, or, are significantly impacted stakeholders being ignored?

- What difference does / will it make? What is the outcome of the stakeholder engagement and how does this impact on other aspects of the organization’s performance, and, how does it benefit the organization and its stakeholders?

## Stakeholder Involvement in the Content Development Process

As has been described above, there are significant benefits to the organization, its services and products from having a strategy and process for stakeholder engagement.

With respect to the development and maintenance of the international release of SNOMED CT; stakeholder engagement is of particular importance as it will enhance the IHTSDO’s ability to ensure that the clinical terminology is fit for the purpose of underpinning the individual’s electronic health record.

It is only by engaging with a wide spectrum of clinical professions, health informaticians and clinical system vendors that the content will be comprehensive, scientifically validated and is safely applicable across all national and international boundaries.

However, the act of ‘content development’ spans a wide spectrum of activities and can have varying degrees of impact on users and vendors. Therefore, the level of stakeholder engagement needs to be in proportion to the anticipated impact of the change. Changing a description from its plural to singular form may have little impact compared with the impact of the anatomy redesign project and so the level of stakeholder engagement must be chosen appropriately.

The IHTSDO is accountable to its members both for the content of SNOMED CT and how it directs its resources and so for each instance of stakeholder engagement the following question should be addressed: for a given content development project “Do the benefits of undertaking stakeholder engagement outweigh the costs, including both tangible and intangible costs associated with the potential negative impacts of not doing it”?

The proposed Stakeholder Engagement Process outlined below is intended to support members of the content development team in achieving a level of stakeholder engagement appropriate to the content development project under consideration. Stakeholders will be provided with timely feedback and on the outcome of their involvement and the process will provide an opportunity for stakeholder feedback to ensure openness and transparency.

# Stakeholder Engagement Process

## Introduction

Although the IHTSDO does not currently have a formal process for stakeholder engagement within the content development process, engagement does occur as part of the request submission process and within the special interest and project groups.

The goal of a Stakeholder Engagement Strategy is to adapt and formalize these processes to involve and engage relevant stakeholders in the content development process, giving them the possibility to contribute to the different stages of the process, from the initial understanding of the problem, through the development and construction of a solution(s), to the adoption of the solution by the user community.

In the following sections we will explore a methodology for identifying an appropriate level of stakeholder engagement based upon an assessment of the impact of the content development project on users and vendors.

The remainder of this section follows the steps identified within the stakeholder engagement process diagram and the numbering of the chapter subsections correlates with the numbering on the diagram.

## Content Development Project Initiation

The source for all content development projects will be the IHTSDO Content Development Tracker on CollabNet. These projects will normally involve the need for new or amended editorial policy, changes or enhancements to the concept model or alignment of existing content to editorial policy. Each tracker item will be assigned to an individual or lead author by either the Chief Terminologist or Content Development Manager.

Some projects require only minor changes or the addition of small numbers of non-contentious concepts etc. In these instances the editor may agree with the CT or CDM that only normal peer review and sign off will be required and no formal stakeholder engagement is required. This should be formally documented within the project documentation

The assigned editor will then follow the agreed Content Development Process. With respect to the stakeholder engagement process the editor must first decide whether the content development project is considered appropriate to be progressed as a ‘Fast Track’ project. If it is, formal external stakeholder engagement will not be required and the project will continue with peer review and feedback to the requestor.

## Define Purpose, Scope and Desired Outcome of Stakeholder Engagement

In order to be able to assess the effectiveness and outcome of the stakeholder engagement process it is essential to formally define the purpose, scope and desired outcome. A set of clear statements documented at this stage of the project will assist the stakeholders in understanding their role and provide the IHTSDO a basis upon which they can assess the return on investment (cost of engagement vs. documented improvement in SNOMED CT content).

Each content development project is likely to have a unique set of statements to support the purpose, scope and desired outcome, however, in order to support users a number of examples are given below:

  - Diabetes Complications – Review of attributes ‘associated with’ and ‘due to’

  - Purpose: To clearly define the use of the attributes of ‘associated with’ and ‘due to’ and produce updated editorial guidance

  - Scope: Restricted to the complications of diabetes mellitus

  - Desired outcome: An agreed set of diabetic complications modeled using an agreed interpretation of the use of the attributes ‘associated’ with’ and ‘due to’ and updated editorial guidance which is implementable by editors/authors

  - Representation of anatomy.

An academic center reported that within SNOMED CT ‘Low back pain’ is inferred as a kind of ‘Abdominal pain’ as a consequence of the propagation of attributes along the actual hierarchical tree of ‘Abdominal structure’.

  - Purpose: To model correctly the different anatomic entities, align with the FMA model and revise the current structure

  - Scope: Restricted to modeling of the lumbar region and abdomen

  - Desired outcome: Correct Part-whole representation and reasoning. ‘Low back pain’ is not inferred as a kind of ‘abdominal pain’

  - Non-human subset project

  - Purpose: To improve the quality, completeness and utility of the non-human subset

  - Scope: Restricted to non-human (veterinary-only) concepts

  - Desired outcome: A consensus on the definition and scope of the non-human subset. Agreeing on a practical and systematic way to identify and organize existing non-human concepts. Going forward, finding a better way of maintaining the non-human subset

It is important to ensure that the desired outcomes are measurable and the stakeholders are appropriate for the project and its desired outcome.

## Assess the Project Risk Profile

Not all projects require the same level of stakeholder engagement and not all stakeholders for a given project require the same level of engagement. When determining the appropriate level of stakeholder engagement, the following three (3) main factors should be considered:

- Impact – Determining the impact of a particular change is not always straight forward and is often multifactorial, but in general the following is a guide:

  - High impact:

    - Significant numbers of concepts affected

    - Significant number of users affected

    - Significant changes to vendor software required

    - Significant change to concept model

    - Significant change to content development software or processes

  - Low Impact

    - Small number of concepts affected

    - Small numbers of users affected

    - No changes to vendor software

    - No change to concept model

    - No change to content development software or process

When identifying the level of impact account should also be taken of the indirect consequences for National Release Centers (NRCs) where editorial decisions previously made by the NRC are impacted by a change to editorial principles by the IHTSDO.

- Controversy level – Changes that are more controversial generally require a higher level of stakeholder engagement. Correction of spelling mistakes or deviations from naming style guidance is not usually controversial and requires minimal stakeholder input. More controversial projects will require and benefit from the input of more stakeholders.

The existence of multiple, equally sound but significantly different solutions to a problem generally indicates a high level of controversy. This is also true when multiple groups express strong and radically different opinions on a particular proposal. It is possible that a higher than expected level of controversy only becomes apparent after the process of stakeholder engagement has started.

- Urgency – a case can be made that for more urgently-needed changes, such as the addition of a new and important disease concept (e.g. SARS), the requirement of stakeholder engagement can be lower because of practical constraints

The priority (or importance) of a project as recommended by the Content Committee and/or specified by the Management Board, in itself does not determine the required level of stakeholder engagement. High priority projects can have high or low impact, and, high or low controversy level, which will therefore accordingly have a higher or lower requirement for stakeholder engagement.

It is recommended that the IHTSDO trial a risk analysis approach assessing the impact of the proposed changes as suggested below:

- For impact level allocate each of the following criteria a score of 0 – 3

  - numbers of concepts affected

  - number of users affected

  - changes to vendor software required

  - change to concept model

  - change to content development software or processes

- Divide the result by 5 and round to the nearest whole number

- Assess the controversy level on a score of 0 – 3 where 0 is minimal controversy and 3 indicates controversy at Government or International Professional level.

- Plot the resultant score and then use the derived risk level to identify the level of stakeholder engagement as suggested in the stakeholder engagement matrix in section 3.5 below.

| Controversy Level | 3 |  |  |  | High Risk |
| --- | --- | --- | --- | --- | --- |
|  | 2 |  | Medium |  |  |
|  | 1 |  |  | Risk |  |
|  | 0 | Low Risk |  |  |  |
|  |  | 0 | 1 | 2 | 3 |
|  | Impact Level |  |  |  |  |

Project Risk Profile

The urgency factor is not included here as urgent cases are quite rare. When they occur, the requirement for stakeholder engagement should be lowered to what is practical according to the circumstances.

In addition it should be recognized that the intent of content development is to ‘improve’ the quality and consistency of SNOMED CT. Where controversy is high due to differences of opinion on what is considered to be the ‘correct’ approach, it may be necessary to choose an option which is less ’pure’ but which improves quality and consistency rather than do nothing. By creating consistency it is then possible to incrementally revise the consistent content at a later date.

## Select Method of Stakeholder Engagement

The method of engagement needs to be in proportion to the perceived impact of the project on users and vendors, for reasons of cost efficiency and in order to promote speedy resolution of the issue. Therefore we would expect significant changes and/or high impact changes to require the highest level of stakeholder input and possibly face to face engagement while minor changes may only require a few well targeted email responses.

There are a number of different ways in which the methods of engagement can be categorized, but for the purposes of this exercise we will use direct and indirect.

Direct engagement will be defined as being any engagement in which the expectation will be that the members are involved in real time verbal exchange, e.g. face to face meetings, whereas indirect engagement will be defined as where the participants do not engage in real time exchange e.g. responding to email surveys etc.

Note: that while list servers may result in real time exchanges, because the system supports exchange of emails over a period of time it is not considered to be a form of direct engagement.

For each of direct and indirect engagements we can further categorize by engagement type:

- Inform – participants receive notification by email or are directed to a collaborative site where information is shared. A response from the stakeholders is neither expected nor required.

- Consult – A dialogue between the IHTSDO and stakeholder takes place. This may be a request for feedback to a proposed change, completion of a survey etc.

- Involve – Active participation either by individuals or groups, such as special interest groups. Participation is likely to be without cost to the IHTSDO unless an external facilitator is involved.

- Collaborate – Active participation by individuals, groups or organizations in which there is an agreement to deliver a program of work often on a contractual basis.

There are many ways of tailoring the method of engagement to the goals and desired outcomes of the stakeholder engagement process. Below is a listing of some of the methods that the IHTSDO may consider, a number of which are already in use:

- Online collaborative space

  - Interactive with stakeholders, post projects, educate/FAQs, recruit participants, conduct forums, topic-specific, set up briefings, open comment period, etc. (may need skilled facilitator)

- Online (virtual) communities

  - Voluntary participants who join based on their interest in a particular topic (list serves, LinkedIn groups, distribution lists, and hold virtual meetings). Could also include soliciting input from working groups for specific focus areas (like pharmacy, event-condition-episode, observables, implementation)

- Grassroots effort

  - Start a local, ground-up SIG to spread awareness/recruit participants

- Collaborative research

  - Work directly with stakeholders at different stages (e.g. impact analysis, consensus on assessment, etc.)

- Product development challenges

  - Vendors/developers compete for reward (prize/money) to develop products/create ideas for dissemination and implementation

- Direct outreach

  - Contact stakeholders directly (in-person interviews, emails, and phone calls), set up focus groups and advisory panels

- Indirect outreach methods

  - Target membership lists from professional associations and organizations to identify clinicians/other stakeholders (“requests for participation”), postings on Web sites, blogs and newsletters; bulletins, referrals through existing stakeholders, use social media to disseminate outputs/elicit feedback

*in some cases, it may improve breadth of involvement if stakeholders may receive honoraria/incentives for participation

- Other

  - Questionnaires

  - Online surveys

  - Feedback forms

  - Social media (to disseminate info)

  - Post links (on partner websites)

- Research methods (no direct stakeholder contact) may include:

  - Peer-reviewed literature, best practices – primary method for disseminating research findings

  - Online surveys Review existing classifications, review other ontologies

Any one project may employ a number of different methods of stakeholder engagement and the authors propose that the IHTSDO pilot a matrix approach to combine engagement ‘method’ with the engagement ‘types’ to ensure an appropriate level of engagement for the predicted risk associated with the impact of the change as outlined below:

| Engagement Method | Direct > 10 users/ Groups Inform | Direct > 10 users/ Groups Consult | Direct > 10 users/ Groups Involve | Direct > 10 users/ Groups Collaborate |
| --- | --- | --- | --- | --- |
|  | Direct < 10 users/ Groups Inform | Direct < 10 users/ Groups Consult | Direct < 10 users/ Groups Involve | Direct < 10 users/ Groups Collaborate |
|  | Indirect > 10 users/ Groups Inform | Indirect > 10 users/ Groups Consult | Indirect > 10 users/ Groups Involve | Indirect > 10 users/ Groups Collaborate |
|  | Indirect < 10 users/ Groups Inform | Indirect < 10 users/ Groups Consult | Indirect < 10 users/ Groups Involve | Indirect < 10 users/ Groups Collaborate |
|  | Engagement Type |  |  |  |

Project Engagement Approach

The coloring of the matrix carries the same meaning as in the project risk profile: red indicates high risk, yellow medium risk and green low risk. In the diagram above, a risk analysis has put the project medium risk indicated by the blue circle. This is relatively high risk within the medium risk section and therefore it is suggested that this warrants active direct involvement with less than 10 users and/or groups.

This approach is experimental and will need refinement with use and feedback. The boundaries of the engagement method and type are likely to be blurred and individual project leaders will need to make a judgment as to what is most appropriate for their circumstances.

When applying this approach to the formal content development process it is envisaged that the method and profile of the stakeholder engagement is likely to change according to the stage of the development. As an example; for a content development project which is considered to be of medium risk.

- Inception phase:

  - Inform, by email, an appropriate number (<10 individuals and/or groups) of domain experts that there is a proposed change to a hierarchy of interest to them along with an explanation of the issue to be addressed. Seek their input into reviewing the proposed options for resolution.

- Elaboration phase:

  - Hold an online meeting to share the options for resolution and gain feedback on the preferred option.

- Construction phase:

  - Liaise with the stakeholders for the elaboration phase, sharing the result of the editing at a face to face focus group and seek feedback and request volunteer users and vendors for piloting. By agreement with a selected number of users and vendors pilot the solution and get feedback via CollabNet.

- Transition phase:

  - Check that the specific Use Case has been satisfied

  - Inform the wider community of practice of the changes and seek user feedback via a list server.

## Identification of Stakeholders

The Glossary defines Stakeholders as “those individuals, groups of individuals or organizations that affect and/or could be affected by the organization’s activities, products or services and associated performance with regard to the issues to be addressed by the engagement”.

This section will explore activities to be done in the context of stakeholder engagement as an aid to content development, and based on this; identify who the key stakeholders are and what roles and responsibilities they may have with respect to the Content Development Process.

### Engagement Activities of Stakeholders

The goal of SNOMED CT is to provide ‘ a common language that enables a consistent way of capturing, sharing and aggregating health data’.

No single terminologist can grasp the whole, constantly evolving healthcare domain, neither explore in detail if and how this domain is referenced within SNOMED CT.

Those who use SNOMED actively or explore SNOMED systematically will be the primary source for reporting potential omissions and errors in relation to concepts, semantic definitions, logical inferences, weak subtype relationships, textual descriptions and translations and must be encouraged to report these through the request mechanism.

The community of practice, clinical professional organizations, vendors and content development special interest/project groups within the IHTSDO will be working systematically on expanding and restructuring content either as a part of an organized program of work or in response to specific use cases.

These complementary activities will result in both internal and external stakeholders who participate in a dialogue with the Chief Terminologist and Content Committee in order to leverage the quality of the SNOMED CT. This process must be actively managed in order to ensure that those who actively contribute to the development and maintenance process also receive adequate and timely feedback from the IHTSDO on the progress of their contributions.

### Stakeholder Identification and Analysis

Based on the defined engagement activities and whether the stakeholders interface to activities inside or outside the IHTSDO organization, it is possible to identify groups of internal and external stakeholders.

“Internal” stakeholders may originate from several IHTSDO organizational structures. Generally, “External” stakeholders are found within the wider global Community of Practice of SNOMED CT users and others.

The clear distinction between “internal” and “external” is sometimes artificial and may not always be easy to distinguish. “Internal” may be limited to the examples in the first row below. Perhaps everyone else is part of the immediate and wider IHTSDO “Community of Practice”. There may be a temporal aspect as well – it is possible that individuals and organizations may be external stakeholders in some instances and internal in another. However, the distinction is useful and will be used to determine the roles and responsibilities identified within the tables below.

| Type | Description | Examples |
| --- | --- | --- |
| “Internal” | IHTSDO Staff | - Chief Terminologist and other IHTSDO Officers - Content Development Manager - Consultant Terminologists - Others |
|  | IHTSDO Governance Bodies | - General Assembly (GA) - Management Board (MB) |
|  | IHTSDO Advisory Bodies | - Harmonization Bodies - Member Forum (MF) - Affiliate Forum (AF) |
|  | IHTSDO Standing Committees | - Content Committee (CC) - Implementation & Innovation Committee (I&I) - Quality Assurance Committee (QAC) - Technical Committee (TC) |
|  | IHTSDO Work Groups | - Special Interest Groups (SIGs) - Project Groups (PGs) |
|  | IHTSDO Contracted Information Technology solution developers and Suppliers (“Vendors”) | - For example, those involved in the development of the collaborative editing functionality in the IHTSDO Workbench. |
|  | National Release Centres |  |
| “External” | Health Informaticians | - Health Informatics Associations and related media publications |
|  | Strategic Partners | - Harmonization bodies, other Health Information Standards Development Organizations (SDOs), etc. |
|  | Healthcare Providers | - Academic Centres, Centres of Excellence, Hospital groups, Clinics - Health and social care professionals |
|  | Professional Associations / Speciality Groups | - Licensing, Accreditation Bodies - Associations / “Domain” Specialties (i.e. Pharmacology, Pathology, Biology, etc.) |
|  | Government organizations | - Department/Ministry of Health - Advisory, expenditure planning and oversight committees |
|  | Healthcare Information Technology solution developers and suppliers (“Vendors”) | - For example, those involved in the development and supply of other applications used for terminology browsing, editing etc. - Clinical System/EHR developers |

List of “Internal” and “External” stakeholders

The “internal” stakeholders are well known to the IHTSDO and may be either employees, form a part of the IHTSDO governance process or are members of one of the committees, special interest or project groups. The internal stakeholders may be either those who identify areas of SNOMED CT for change or those who develop and implement the requested change, or in some instances, both.

The “External” stakeholders may also act as either those who request change or at the request of the IHTSDO, form a part of the stakeholder engagement process, providing feedback and access to their specific domain knowledge.

The identification of appropriate “External” stakeholders however, by definition, is far less clear and the danger exists that some important contributors may be inadvertently excluded or overlooked. It is also possible to engage more stakeholders than is necessary or appropriate for the specific development project that may result in too many diverse opinions or an unacceptable delay to the resolution of the issue.

An important step in the stakeholder engagement process is establishing the profile and mix of stakeholders to match the content development project in such a way as to ensure the goals of the engagement process are achieved. In addition to ensuring the right knowledge and skill mix is achieved account must also be taken of the stakeholders willingness and ability to engage and their likely impact, both positive and negative, on the process and their peers.

Key to achieving the goals set within the stakeholder engagement process is management of stakeholder expectations. There must be a clear explanation that their input, while highly valued, forms a part of the process of issue resolution and any decision to include or exclude their recommendations rests with the Chief Terminologist and the IHTSDO. In order to ensure ongoing engagement and to promote trust between the stakeholders and IHTSDO there must be regular and timely feedback on the progress and outcome of the engagement process and resolution outcome. This is just as important for internal as well as external stakeholders.

### Roles and Responsibilities

Based on the discussion above we are able to specify the following roles and responsibilities in order to initiate and manage stakeholder engagement.

| Role | Responsibility | Task |
| --- | --- | --- |
| Facilitator (this could be either the assigned terminologist or IHTSDO support role (CDM)) | Stakeholder Engagement Strategy | - Initiating the process |
|  |  | - Communicating the process to stakeholders |
|  |  | - Allocating necessary resources |
|  |  | - Defining quality indicators |
|  |  | - Evaluating and adapting the process |
|  | Define Request and Response dialogue | - Refusal and/or acceptance criteria for a request. |
|  |  | - Defining stakeholders profile attributes |
| External stakeholder | Defining terminology content | - Submitting request change or addition - Evaluating and responding to request for consultation and advice |
| Internal stakeholder | Defining terminology content | - Broadcasting request for advice |
|  |  | - Receiving response |
|  |  | - Monitoring incoming request |
|  |  | - Informed refusal |
|  |  | - Acceptance and initiating tracking system |
|  |  | - Terminologist assignment and review of documents |
|  |  | - Review of Inception and Elaboration phase documents |
|  |  | - Initiating Construction and Transition phase. |
|  |  | - Formulating request for advice on terminology issues |
| Consultant Terminologist | Implement Inception and Elaboration phase | - Analysing stakeholder’s profile |
|  |  | - Estimating project impact |
|  |  | - Initiating review by stakeholders |
|  |  | - Defining problem and proposing solution |
| Editor terminologist | Implement Construction and Maintenance phase | - Implement and maintain proposal. |
| Project Management | PM of Inception, Elaboration, Construction and Maintenance phase |  |

# Optimizing Stakeholder Engagement

## Criteria for Successful Stakeholder Engagement

The objective of stakeholder engagement as it relates to the ongoing development, maintenance and uptake of SNOMED CT is to deliver effective, sustainable, quality content development by involving relevant stakeholders at appropriate points throughout the IHTSDO Content Development Process. Without engaging stakeholders, there may not be a common agreement or support for a particular content development project. Content development activities are more likely to succeed, especially in the long-term, if they take into consideration the needs of the stakeholders affected by them.

In order to be able to assess and evaluate the success of the stakeholder engagement process during and at the end of the project, the following two sets of criteria need to be defined:

- Definition: this set of criteria deals with how the success of stakeholder engagement can be defined, without necessarily being concerned about how it can be measured.

- Measurement: this set of criteria is concerned about indicators to measure the success of stakeholder engagement, based on how it was defined in the set of criteria mentioned above.

### Criteria to Define Successful Stakeholder Engagement

As mentioned above, the objective of stakeholder engagement is to deliver effective, sustainable, quality content development by involving relevant stakeholders at appropriate points throughout the IHTSDO Content Development Process. Therefore the success of stakeholder engagement can be defined in two main axes:

- Its contribution to the success of its corresponding content development project, by ensuring that the best possible solutions are pursued; and

- Its positive effect on worldwide adoption and use of SNOMED CT, through

a) ensuring the solutions are aligned with stakeholder needs

b) giving the stakeholders a sense of involvement and ownership.

The abovementioned two axes can be broken down into the following points. The following points can describe what the success of a stakeholder engagement process entails.

- Quality of articulating the problem for stakeholders

- Quality of proposed solution

- Choice of the level of engagement

- Initial list of stakeholders to engage: how well was the list prepared; how well was the balance between too many and too few maintained; how close was the initial list to the “ideal list” (ideal list being one that would be created if the project owner knew of all important stakeholders).

- Inclusion of additional stakeholders as required: how well did the project owner manage to revise the initial list as the engagement process progressed; how close is the revised list to the ideal list?

- How well did the project owner led through the engagement process:

  - Communication

  - Leadership and facilitation

  - Consolidation of feedback

  - Creative modifications to the proposed solution if needed, to contribute to the success of the project and satisfy stakeholders.

### Criteria to Measure Successful Stakeholder Engagement

While the criteria listed above are not necessarily measurable, the following criteria are suggested to be qualitative or quantitative indicators to measure the success of a stakeholder engagement process:

- Did the content development project meet its own objectives?

- Did the end product meet stakeholder demands?

- Percentage of stakeholders who participated, to stakeholders initially invited for consultation.

- Did the stakeholders that were initially invited, identify/recommend additional stakeholders?

- If the answer to the above question is yes:

    - Were the additional stakeholders invited for consultation?

    - Percentage of additional stakeholders who participated, to all additional stakeholders that were invited for consultation.

- Percentage of stakeholders who identified the project as their priority area, or as a project that will affect their work.

- Percentage of stakeholders that believe the final product will have a positive impact on them.

- Did stakeholder engagement require a reasonable level of effort?

- (number of stakeholders that their input aligns with the final outcome of the project) divided by (number of stakeholders who provided input)

- Quality of stakeholder input.

- Positive feedback from stakeholders about the ease of communications and level of engagement they experience.

It is suggested that during a content development project, the person leading the project should periodically evaluate the success of the stakeholder engagement process that is being pursued, and consider corrective actions where poor engagement or failure to meet objectives is identified.

Also, it is recommended that at the end of project, its success in terms of engaging stakeholders be measured and documented. This level of success could be one of the important indicators for the overall success of the project.

### Criteria to Determine When Stakeholder Engagement Has Been Successfully Completed

It is important to ensure that the stakeholder engagement process is enabling – both for the IHTSDO organization and for the stakeholders.  The SNOMED CT content development process must not be unnecessarily prolonged, and the time expended by both content developers and stakeholders must remain productive, so criteria are required for determining when to end the stakeholder engagement process for a specific project.  The following primary criteria are suggested:

- Adequate length of time spent on stakeholder engagement.

It is obviously necessary to spend adequate time in engaging with the various stakeholder participants and organizations to achieve the desired quality, both of the engagement process and ultimately of SNOMED CT itself.  But spending excessive time in stakeholder engagement will divert resources from other tasks (with potentially even higher priority), and may therefore actually decrease the overall quality – so the proper balance needs to be determined and maintained.

- Adequate number individual participants in the stakeholder engagement process.

If only a few individuals are participating in the stakeholder engagement process, the needed breadth of experience and perspectives may not be represented, with a risk of lower quality of both the process and ultimately of the resulting changes made to SNOMED CT.

- Adequate number of organizations represented in the stakeholder engagement process.

Analogous to #2, if only a few stakeholder organizations are participating in the engagement process, the needed breadth of experience and perspectives may not be represented, with a risk of lower quality of both the process and ultimately of the resulting changes made to SNOMED CT.

- Adequate degree of achievement (both in number and extent) of the stakeholder engagement process success criteria (listed in 4.1.2 above).

It is expected that the larger the number of the achieved (depending on how the thresholds for achievement are defined) success criteria, the greater will be the ultimate quality of the results of the stakeholder engagement process.  As more experience is gained, the success criteria (and the success thresholds determined for each criterion) will undoubtedly be refined, likely improving the ability to meet this expectation.

The levels that are considered to be “adequate” will vary depending on the size and scope of the project.  Obviously, large, complex projects are likely to require a more extensive and longer duration stakeholder engagement process than will smaller, simpler projects.  It is premature at this time to specify precise metrics for determining the desired endpoint for the stakeholder engagement process, but it is expected that as experience is gained over time it will be possible to establish appropriate metrics to establish this.

### Potential Additional Quality Indicators for Adequate Stakeholder Engagement

Some proposed quality indicators for consideration include:

- Positive relationships between the IHTSDO and external stakeholder.

- Positive publicity about the IHTSDO and SNOMED CT.

- Increased levels of contribution to the development of SNOMED CT.

- Positive feedback from parties collaborating with the IHTSDO about the ease of communications and level of engagement they experience.

As experience is gained in the stakeholder engagement process, one or more of the above indicators, and potentially others, may be further developed and implemented as quality criteria.

## Potential initial activities to support stakeholder engagement

The following is a list of ideas that may be considered by the IHTSDO to start development of a network of clinical advisors/stakeholders to support stakeholder engagement:

- On the IHTSDO project home page have a section similar to the “Latest Workbench News” which details current documents out for review- with due dates.

- Notify the NRC’s (via the Member Forum), current users and other interested organisations or individuals with an email of what’s in development (so they know what’s coming up) and out for review. You wouldn’t want something for every document rather a weekly/ fortnightly summary. Thought- would this mean that docs should be released for review say twice a month with two weeks for feedback given? I suggest we ask via the member forum how their NRC’s or relevant organisations would see this happening.

- Emailing the community of practice to ask if there are clinical people who’d be willing to be contacted in relation to reviewing content projects for their area of expertise. Care would need to be taken not to overload those who volunteer. The list could be kept as simple register accessed by those doing development work.

- Place a question in the FAQ section on the collaborative site for the community of practice on being involved

- Update the “How can I help to improve SNOMED CT question in the FAQ section on the IHTSDO website with how to be involved in content reviews.

- Determining national and international peak bodies and approaching them in relation to providing input into terminology development- this may be providing clinical advice and/or reviewing documents. This could be raised via the Member Forum for national bodies.

- Have a session in the next showcase about supporting content development-not the process of development itself but how to be involved.

# Summary

The purpose of this document was to provide a framework for stakeholder engagement which would support the Content Development Process. The authors have presented a proposal which represents a first attempt at defining a process which should aid authors and editors in choosing a level of stakeholder engagement which is appropriate to the impact and risk of that project.

This approach has yet to be piloted but it is hoped that the next group of Consultant Terminologists will try and implement the process as part of their content development projects, provide feedback on, and update the process so that it can become a useful tool.

If successful, this approach could be adapted for wider use within the IHTSDO and by National Release Centers.

# Appendix A: References

There are a number of frameworks and standards which organisations can draw on to provide guidance for the process of stakeholder engagement, and, which aim to improve the sustainability performance of the organisation.

- The AccountAbility 1000 Series which includes the AA1000 Stakeholder Engagement Standard (AA1000SES) and the AA1000 Assurance Standard (AA1000AS) are generally regarded as amongst the most useful and are found at www.accountability.org and at www.accountability.co.uk. The most recent version of the AA1000 Stakeholder Engagement Standard 2011, Final Exposure Draft is available for download as a PDF document via the link at http://www.accountability.org/about-us/publications/aa1000-1.html

It provides a principles-based, open-source framework for quality stakeholder engagement and supports the AA1000APS Principle of Inclusivity. It can be used as a "stand-alone" standard, or as a mechanism to achieve the stakeholder requirements of other standards, including GRI G3 and ISO 26000.

- AA1000SES was also used to provide the framework for the development of The Stakeholder Engagement Manual, Volume 2: The Practitioner’s Handbook on Stakeholder Engagement (ISBN 1 901693 220). This is located at www.accountability.org.uk and can be downloaded at http://www.accountability.org/images/content/2/0/208.pdf

- The Quality Assurance Committee Terms of Reference is available from IHTSDO website at: http://www.ihtsdo.org/about-ihtsdo/governance-and-advisory/standing-committees/qa-committee/

- Information about the IHTSDO Quality Assurance Framework is found at: http://www.ihtsdo.org/develop/quality-assurance/quality-guidance/

http://www.accountability.org/images/content/3/6/362/AA1000SES%202010%20PRINT.PDF

http://www.accountability.org/images/content/3/6/362/AA1000SES%202010%20PRINT.PDF

http://www.accountability.org/images/content/3/6/362/AA1000SES%202010%20PRINT.PDF