# Sharing translation into a language across multiple countries

This section is fed by the current project of translation to French language across NRCs of countries hosting a large French speaking community. This project joins forces from the NRCs of Belgium, Canada, France, Luxembourg and Switzerland. France not being a member yet, the role of NRC in this country is temporarily played by Phast.

Furthermore, the issues tackled with in this section might be considered for other languages as well, such as Spanish Portuguese …

The sub-sections below delineate the various stages for such a project. These stages should be accomplished in sequence although a certain degree of parallelism is possible for some of them.

## Prerequisite: A recognized common authoritative framework for the language

Such a project of consolidated translation across several countries is worthwhile if and only if the language has a high degree of universality: the language is recognized as common across countries using it and is backed by a set of living authoritative organizations and documents that shape the language grammar and spelling and provide a universal base for its vocabulary.

This common authority does not preclude further local enrichment to the common vocabulary, with additions specific to one country or the other.

This condition is fulfilled for the French language, for which the Académie française and a handful of other bodies are recognized as the authorities, which accompany the evolution of the language.

In case the condition is not fulfilled for another language – say English, which has more than one source at least for spelling – then the project stops.

## Starting point: Existing national translations – prepare the merger

The project of building a single translation towards a language used by several countries usually arises when some of these countries already have an ongoing translation project within their national territory. Therefore, the project starts in most cases with an assessment of the already existing translated terms and translation processes. The aim of this first stage is:

- Assess and compare the existing national editorial and linguistic guidelines and prepare their merger into a single editorial and linguistic guideline for the language, backed by the authoritative rules and by the SNOMED translation and editorial guidelines.

- Assess the degree of local variations in vocabulary, and define a strategy to accommodate these variations, for instance by producing a sufficient number of synonyms to accommodate the needs of each country, and opening the possibility of localization of the choice of acceptabilityId (preferred / acceptable).

- Once the common editorial and linguistic guideline is approved by all parties, realign each existing local translation with this guideline, applying the strategy defined to accommodate geographic variations of vocabulary.

## Version 1: Merger of the realigned existing descriptions

- Set up a cooperative process across NRCs for integration of the national descriptions into a single common description file, discarding redundant descriptions and checking the linguistic and editorial validity against the new common guideline, as well as the usability. This step includes the attribution of roles of author, linguistic reviewer, usability reviewer, and the definition of a process to arbitrate the hard cases.

- Execute the process: Merge the national descriptions into the single shared corpus of descriptions.

## Version 1: Manage preferences in language refset at global and national levels

- Assess the commonalities of preferences of terms across the countries and infer a strategy for management of the acceptabilityId attribute:

  - If there is a consensus on preferred terms for a significant part of the merged translation then it is worthwhile to define a common language refset file, which can be further localized by national NRCs to handle their exceptions of preferences by adjusting the value of acceptabilityId.

  - If no consensus at all on preferred terms, then the language refsets will be defined locally by each NRC. However all of them still include the same corpus of descriptions in the common language.

## Publish version 1 and set up the long-term organization and process for maintenance

- Choose the edition of SNOMED CT that should convey the common translation for the language. Since the translation is the cooperative work of multiple countries the target edition is likely to be the international edition.

- Discuss across NRCs and with SNOMED International in order to identify a sustainable organization, which can endorse the liability of the common translation over the long run.

- Define the maintenance process for the translation.