# Translation preparation

The planning issues described in section 2 are common for the entire translation project. However, for practical reasons all concepts cannot be translated simultaneously. Moreover, if you lack sufficient resources to translate SNOMED CT entirely, you will have to determine one or more subsets with which to start. The preparation therefore includes the selection (creation, allocation) of specific translation subsets.

## Translation subset selection

The aim of subset selection is to provide translators and reviewers with the best possible prerequisites for their work. The translator might for example want to work with concepts within the same subject field, e.g. heart conditions including body structures, disorders and procedures.

The choice of order of areas to be translated can be vital for other parts of the process of introducing SNOMED CT to health and social care. Different approaches for identifying the initial subsets can be chosen depending on local needs. For example, one could give:

- Priority to concepts which recur, link, qualify and confer meaning to other concepts in different contexts, e.g. body structures and qualifier values. Translating such concepts first maximises re-use of translations, which increases both efficiency and consistency.

- Priority to concepts which are relatively easy to translate, because they are similar and/or well-defined – for the same reason.

- Priority to concepts which are to be part of pilot projects in a given health or social care context, or part of a specific research project – especially if your resources are limited.

Selection of subsets is preferably managed by a team including specialists in health and social care, terminologists and experts on SNOMED CT.

Add section on use of translations from external sources; e.g. from different NRC’s, or from different code systems such as Orphanet. Trust and source

# The translation process

There is not a single best workflow to recommend for SNOMED CT translation. Many different workflows are possible. The workflow most suitable to your needs depends on what part of SNOMED CT you mean to translate, the resources (include translators) you have and the order in which you prioritise your translation principles.

## Team selection

It takes a village to translate SNOMED CT, that is to say a group of people with different roles and expertise:

- Terminologists ensure the semantic correctness of the translations: to check whether the translations convey and imply the exact same meaning as the concepts expressed with English descriptions. They should also liaise with SNOMED International to discuss discrepancies between English descriptions and concept definition and to report duplicate concepts.

- Healthcare professionals, as the target users of the translations, should indicate which translations are most frequently used and recognisable.

- SNOMED CT contains many concepts that refer to procedures or disorders that are highly specialised, have become obsolete, or convey the same meaning through entirely different descriptions. No single healthcare professional or terminologist can interpret them all. You will need a team of specialists from all healthcare disciplines, who can indicate what an obscure term means, how it is referred to in your country and whether it is relevant for your country.

- Linguists are required to ensure consistent, concise, grammatical translations that are free of spelling errors and avoid non-medical translation pitfalls. Translation, especially in such huge quantities, is a profession in itself: a group of healthcare professionals simply will not make as neat a job of it. By preference, the translators should be specialised in medical translation or assisted by a medical linguist.

Some of these skills may be combined. In the Netherlands we have found it useful to train young Medical Doctors in the use, purpose and structure of SNOMED CT, so they can check both semantic correctness and recognisability of the translation, killing two birds with one stone. Alternatively, you could train the translators as terminologists, or search for healthcare professionals with a linguistics background. However, combining multiple skills or expertise’s in a single person will make it harder to find suitable people and increase the cost of their labour.

## Prioritise the translation principles

The ITHSDO Translation Guidelines discuss the translation principles that are vital to translating SNOMED CT, including the idea of concept-based translation. Translations should be unambiguous, linguistically correct, consistent and both recognisable and acceptable to healthcare professionals. Unfortunately, these requirements conflict frequently. In order to resolve these daily dilemmas most quickly, you should prioritise them and let this priority influence your workflow. If you rate recognisability and acceptability highest, then the healthcare professional should have the final say over each translation. If on the other hand you value consistency and linguistic correctness more, then a medical linguist or translator should have that honour.

In difficult cases an editorial board can ensure consensus about the best possible translation (or compromise). The use of synonyms can be used support different jargons between specialist groups, spelling variants or patient-friendly terms. To distinguish translations that adhere to all principles from those that deliberately violate some (e.g. contain spelling errors, are meant for patients rather than medical professionals, or are ambiguous) you can choose to create multiple language reference sets.

You should also decide in advance how to handle obsolete or erroneous concepts. Do you want to translate them anyway (which leads to an imperfect result), ignore them (which leads to an incomplete translation) or resolve them with SNOMED International (which leads to a large amount of work both for you and for SNOMED International)?

## Determine the workflow

There is no single best workflow. The choices you have made above restrict the number of workflows that are suitable to your situation. However, some principles hold true in all cases:

- Each translation should be concept-based;

- Each translation should be viewed by at least two team members, and any change made, however trivial, should be reviewed by a colleague;

- Each translation should be checked one or more team members with the role(s)of translator, terminologist and healthcare professional;

- You will need an editorial board to maintain linguistic guidelines, correcting any translations that do not comply, and resolve difficult cases;

- You should be able to track the process of each translated concept through the workflow;

- You need some kind of quality assurance (described in “A methodology and toolkit for evaluating SNOMED CT® translation quality”).

Different member countries have translated by very heterogeneous workflows. The previous version of this document recommended the workflow in Figure 1, based on the experiences of Sweden and Denmark.

Figure 1: Translation process recommended after Swedish and Danish translation

This workflow was short and thus efficient, but required translators, reviewers or editors who possessed knowledge within healthcare, linguistics and terminology. In this setup clinical validation is expected to be done in the post translation process.

Conversely, the Netherlands adopted a complex workflow where each expertise owned its own workflow status (see Figure 2). This made it easier to find suitable team members, but increased the amount of time needed per translation and required abundant and careful communication to coordinate the different expertise groups. The Belgian workflow distinguishes two types of reviewers: the domain specialist and the linguist cum terminologist.

Figure 2: Translation process in the Netherlands

Figure 3: Translation process in Belgium

## Progress monitoring and follow-up

The following issues related to the translation process should be monitored and considered:

- Regular adjustment of the linguistic guidelines;

- Adjustment of the resources in the translation processes in order to continuously optimize the process;

- Workflow statistics;

- Correction of translations that do not comply with the linguistic guidelines. This includes changing older translations to comply with a new guideline.

The following issues of project progress should be monitored:

- Follow-up on quantity, e.g. the number of approved translated concepts, the number of unresolved problem concepts sent to the editorial board, the number of errors made by the translators;

- Follow-up on quality, e.g. how well the translation complies with the linguistic guidelines, how well the translation complies with language corpora and concordances of respected medical journals and other relevant sources;

- Follow-up on costs;

- Follow-up on deviations from goals;

- Follow-up on translation service provider issues;

- Follow-up on performance of IT tools.

## Content enhancement

The translation process provides an excellent form of quality assurance for SNOMED CT, both in terms of a review of existing content, and also the identification SNOMED CT concepts which could be added to the release, either as International content additions or by addition to national extensions where these exist. Guidance for content requests can be found here - SNOMED CT Content Request Service. Regarding all requests, whether to the International or National Release, should be supplied with a detailed description of the problem, along with a statement of requirements to inform the resolution. In the case of requests originating from translation activities, this should include details of the problem related to translation with a description including concept/description translations to provide additional clarity.

## Collaborating with other NRCs

## The Translation User Group meets regularly with a dual purpose: to create and update guidelines such as these, and also to share experiences and expertise. When you encounter a particular translation dilemma, such as an ambiguous source concept or term, you can raise an issue in our JIRA project: https://jira.ihtsdotools.org/projects/SCTF/summary .

Any organisation or professional developing a SNOMED CT translation is very welcome to join the group. Details can be found on https://confluence.ihtsdotools.org/display/TRANSLATIONUSERGROUP/Translation+User+Group+Home .

Add section on multilingual translation (or multiple dialects), containing workflow and issues to take into account. Pros and cons of parallel translation vs. sequential.

Add chapter 5: Maintenance of a mature translation